## Basic Example
Import a Single Project
Project "Header" Information |  |  |  |  | Task Information |  |  |  | Skill Assignments
Project: ID | Project: Description | Project: Priority | Project: Project start date (Start) | Project: Project end date (End) | Task: Task type | Task: Description | Task: Predecessor(s) | Task: Duration | Skill: Description | Resource assignment: Units | Resource assignment: Duration
Test | Temporary Project | 3 | 2026-05-15 | 2026-06-05 | Normal | Define Firmware Architecture |  | 4 | System Designer | 1 | 4
Test | Temporary Project | 3 | 2026-05-15 | 2026-06-05 | Normal | Setup Development Environment | Define Firmware Architecture | 2 | System Designer | 1 | 2
Test | Temporary Project | 3 | 2026-05-15 | 2026-06-05 | Normal | Implement Core Firmware Modules | Define Firmware Architecture | 3 | System Designer | 1 | 3
Test | Temporary Project | 3 | 2026-05-15 | 2026-06-05 | Normal | Integrate Hardware Interfaces | Define Firmware Architecture | 2 | System Designer | 1 | 2
Test | Temporary Project | 3 | 2026-05-15 | 2026-06-05 | Normal | Firmware Unit Testing | Define Firmware Architecture | 2 | System Tester | 1 | 2
Test | Temporary Project | 3 | 2026-05-15 | 2026-06-05 | Normal | Debugging & Optimization | Define Firmware Architecture | 2 | System Tester | 1 | 2