## Slide 1: LYNX Project and Portfolio Management Critical Chain Project Management
Integration of Agile and Kanban Workflows – Agile CCPM
Notes: Als we het hebben over projecten dan zien wij dat bedrijven en projectorganisaties zich op zich voorbereiden voor de realisatie van een project. Scope wordt beschreven, rollen en verantwoordelijkheden, risico analyse, governance structuur, etc. Dus je kan zeggen dat organisaties goed voorbereid voor de praktijk / avontuur ingaan. Zo volwassen is men geworden.
Het punt is het blijft een avontuur. Dus alle risico’s die van te voren benoemd waren komen voor. En ook Murphy komt om de hoek kijken. En daar sta je dan. Onze boodschap is: als je dan het avontuur ingaat zorg dat je de juiste instrumenten bij je hebt. Een kompas en GPS, zodat je tijdens je avontuur de juiste beslissing kan nemen en controle over je bestemming kan houden.

## Slide 2: LYNX Overview
LYNX Building Blocks
Levers for improvement (Operations Management for Projects)
LYNX Demonstration:
  LYNX Project and Portfolio Management
“Unconsidered” needs – did you think of…..
  Some examples, e.g. “Vertreterregelung”, run in Debuffered and CCPM mode
  Often initiated by our customers

## Slide 3: The multi-project playing field Objectives and Challenges
Teams
&
Resources
Multi-Project and Portfolio
Project
Optimal Conditions for innovation
Deliver quality
Be able to focus and getting work done
Must be Reliable and Fast
Manage Scope, Time and Budget
Needs to know if the project is on “track”
Satisfy the stakeholders
Portfolio with many projects
High Due-Date performance
Deliver more projects
1. In Time 2. Within budget 3. Deliver Scope 4. Right Quality 5. Across Projects

## Slide 4: A-dato customers presenting at the TOC Anwenderkonferenz 2019, Heidelberg
Presenters:
Römheld
Beekenkamp
SICK
Diamond Air

## Slide 5: TOCPA 2018

## Slide 6: A-dato customers presenting at the TOC Anwenderkonferenz 2018, Heidelberg
Presenters:
Fraunhofer Institut
Holzner & Bertagnolli
Endress+Hauser
SICK
Richard Wolf

## Slide 7: Bosch Mobility Solutions

## Slide 9: Digital Transformation at VIVO (Telefônica Brazil)
Andre Kriger, CIO of Vivo, reveals a mix of critical chain, lean and agile techniques to aggressively double the rate of project deliveries (April 2019)
https://inform.tmforum.org/digital-transformation-and-maturity/2019/04/andre-kriger-cio-telefonica-reveals-mix-critical-chain-lean-agile-techniques-aggressively-double-rate-project-deliveries/

## Slide 11: Fraunhofer

## Slide 12: Diamond Aircraft Industries

## Slide 13: C-JOB

## Slide 14: Endress + Hauser

## Slide 15: Beekenkamp

## Slide 16: Bruns, Exhibitions Shop Floor Workflow Management
Projects:
  Anne Frank Huis
  Over the Edge
  Europe Experience Berlin
  Powerplay, Heilbronn, Germany
Projects:
  Museum for Communication, Bern Switzerland
  FIFA World Football Museum
  Nest, Vevey Switzerland
  In Flanders Fields Museum, Ieper, Belgium

## Slide 17: LYNX TameFlow @ the Shopfloor

## Slide 18: ORTEC

## Slide 19: LYNX TameFlow Task Board Layer 3 Integration Example – including Flow Buffer Management

## Slide 20: LYNX Layers and Building Blocks

## Slide 21: LYNX Workflow Optimization – The Project “Factory”
Stakeholder
„Priority board“
teams
New projects
Layer 1
Multi-Project
Layer 2
Single Project
Layer 3
Workpackages Agile & Kanban
Pipeline & Scenario Planning
Release Wizard
Scenario Wizard
“Strategic Priorities”
Workpackages with Cards
Agile/Kanban Processes
e.g. Sub-tasks / Stories
Projects
CCPM or LFPM
Buffer Management
“Operational Priorities”
Project #1
#2
Project #4
PIPELINE
Project #3
Project # 5
Notes: 3 lagen model. – wat is dan nog een missing link?  kenniswerk. Agile and everything is good.

## Slide 22: LYNX TameFlow Task Board Layer 3 Integration Example – including Flow Buffer Management

## Slide 23: LYNX and LYNX TameFlow
Projects with tasks
Portfolio / Multi-Project
Workpackages with Cards (subtasks, user-stories, cases)
Card
Multi-project resource management
(Skills, profiles, resources, teams, team members)

## Slide 24: LYNX TameFlow Task board with JIRA Issue processing
LYNX TF Team Users
Using LYNX TameFlow Visual Taskboard for Flow Management
JIRA Users
Working on “Issues” (Cards) in JIRA.
LYNX Users
Professional / Light
LYNX TF
JIRA Synchronization

## Slide 25: Collaboration and Team work Working together at the same time in the same project
Projects, tasks, sub-tasks, cards
Resource manager
Team manager
Task manager
Skill/ Resource
Project manager
Portfolio manager
Team member
Just “invite” others in one “click”
“Timing is everything”
There is only 1 moment you can be on time!
If you are not there you are either too early or too late.
Johan Cruijff
A-dato Confidential
External partner

## Slide 26: Observations
Multi-Project Landscape – why change?

## Slide 27: The multi-project playing field Objectives and Challenges
Teams
&
Resources
Multi-Project and Portfolio
Project
Optimal Conditions for innovation
Deliver quality
Be able to focus and getting work done
Must be Reliable and Fast
Manage Scope, Time and Budget
Needs to know if the project is on “track”
Satisfy the stakeholders
Portfolio with many projects
High Due-Date performance
Deliver more projects
1. In Time 2. Within budget 3. Deliver Scope 4. Right Quality 5. Across Projects

## Slide 28: Task Durations (within Projects)
100 %
Wait
Work
Work
Typical
“Flow Efficiency”
Most tasks are not slow, but typically just have to wait a lot.
Work
Work
Work
Work
Wait
Typical task Execution Pattern
Work
Task
10 - 20 %
Notes: Vaak niet boeven 20 % - EERDER ROND DE 5
Zin is krom.  om echtt te verbeteren kan je veel nbeter richten op verminderen van de wachttijden

## Slide 29: Resources are scarce and often not efficiently allocated (spread “thin”)
Limited Resources
Many projects waiting
High Work in Progress
Consequence: Projects fight for resources!
Suboptimal resourcing of projects
(bad) multi-tasking
SETUP
Task project 1
SETUP
Task project 2
SETUP
Task project 3
SETUP
SETUP
SETUP
SETUP
SETUP
SETUP
SETUP
SETUP
SETUP
Multitasking and lack of focus
Dedicated task completion
>3 Times longer duration for project 1

## Slide 30: Waiting Time Multi-Tasking
SETUP
Task project 1
SETUP
Task project 2
SETUP
Task project 3
SETUP
SETUP
SETUP
SETUP
SETUP
SETUP
SETUP
SETUP
SETUP
Multitasking and lack of focus
Dedicated task completion
>3 Times longer duration for project 1

## Slide 31: Constant Changes Variability and Murphy’s law
What would be the duration of a task?
How many/which changes will be required?
Did we think of everything?
What else can happen?
(What can go wrong, goes wrong)
Many deviations from the Plan!
Uwe Techt (Vistem Germany)

## Slide 32: Intermezzo
Een klein testje met 2 taken….
M | U | L | T | I | T | A | S | K
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Het beste brein van Nederland
https://youtu.be/E3bXAzlbA4w
Notes: Multi-Task oefening.
Single task order: 8 to 12 seconds.
Multi-task: 12 tot 20 seconds.
If you have done it richt, there was also an element of quality coming in. What is the next letter to right. A struggle to maintain the quality.
What are the effects:
It took 8 seconds in the first, 12 seconds in the second – that is a 50 % impact on speed and productivy in which we could do the taks done
quality issue. A struggle to maintain the quality.
the first task finsihed after 4 seconds in the first approach, but only after 12 seconds in the second approach. So the duration that took me to do that task, extended dramatically.
So those are the losses: we have a 40 to 50 % loss of productivity, we struggle with the quality and there is certain level of stress that happens, and there is a 2 X or 3 X extension in durations.

## Slide 33
The brain cannot do Multitasking!

## Slide 34: The ASAP Trap Little’s Law
Start Work
(ASAP)
Delays are increasing
Leadtime
Increases
Uncertainty
Murphy
WiP (Work in Progress) is high
WIP (# units)
Output (# units per period)
= Avg. Leadtime (in periods)
Little’s Law
Limited Resources
There are always new projects or there is more work to do.

## Slide 35: Any system needs WIP control….
Cycle time (duration)
Reliability
OUTPUT

## Slide 36: Today and Tomorrow
Parkinson’s law
Student syndrome
Cherry picking
Overload
Multi-tasking
Task Interruptions
Local safeties
De-synchronisation
Kopfmonopole
Early starts
Batching
Roadrunner
Global priorities
WIP Control
  Single tasking
Single-touching
  Global buffers
Late binding
Full-kit
Single-piece flow
  Synchronisation
Desired
Different way of working
Different way of planning
Undesired

## Slide 37: Time for action?
Symptoms:
  Backlog too big
  Long leadtimes
  Unreliable due dates
  High Work pressure
  Poor quality and a lot of rework
  Customers are not happy
  ….
Issues in “Operations Management”:
  A lot of “Work-in-Process”
  Multi-Tasking
  Waiting Times
  Changing priorities
  Many “Top Priority” tasks that are urgent
  Peaks in workload, but also the opposite

## Slide 38: Where to start improving? “Low” hanging fruit
Wait
Work
Most jobs are not slow, but typically just have to wait a lot.
Notes: Overlay met euro tekens, waar zet je geld op in?  groen kost heel veel.

## Slide 39: A different approach… The Critical Chain (Multi-)Project Management Key Ingredients
Buffer
50%
Execute by Single Priority
Traffic light = 1 operational
priority for everybody across projects
Buffer Management
Manage across projects
(Control the WIP)

## Slide 40: Levers for achieving improvements Operations Management for (multi-)project operations
Introduction of Buffer Management with Dynamic Schedules Manage the Buffer
  Aggregate and (re-)move safety time
  Introduction of buffers at strategic positions to absorb uncertainty
Introduction of one single priority and feedback loop  Execute by single priority
  Track progress by Expected-Time-To-Complete (~ ETA)
  Synchronized Execution of Tasks
Introduction of Pipeline and Portfolio Management  Control the WIP
  Constraint based Work-in-Progress management
  Release management (staggering)
Introduction of Aggregation and (dynamic) “Late Binding”  Flexible Capacity

## Slide 41: How to achieve improvements?
Introduction of Buffer Management
Feedback Loop for generating “single” operational priorities

## Slide 42: Psychology of Estimates
Typically >50% durations is a safety buffer
Early completions are rare animals
Many tasks are still late
relative
probability
n days
Safe (2 x n days)
0%
max.
typical estimate
> 80%
achievable
50%
“Laws”:
Available time will always be used (Parkinson´s-Law)
Postponement Behavior (Student-Syndrome)
Murphy will bring a visit
Notes: SPI Index bij Honeywell (Schedule Performance Index)

## Slide 43: Critical Chain Solution Take advantage of Central Limit Theorem
Good Statistics
Central Limit Theorem (add enough things together and everything looks normal)
Notes: Van een normaal plan naar een goed plan – kan allen als dus de taaktijden verkoren en buffer toevoegen.

## Slide 44: Pooling of Contingency – Insurance Model Buffer Management
60
45
10
20
30
40
50
60
Time
Achievable
Contingency
Protect the project (not tasks)
Focus on due-date
“To be safer, (re)move the safety”
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 45: Progress Example 1: 50 % progress on the longest chain / 15 % buffer used
Done
45
10
20
30
40
50
60
Time
50 % / 15 %
Project is on track. The risk that the project will be late is very low.
“To be safer, (re)move the safety”
Done
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 46: Feeding chain detection Always present the right priority during the Execution
Done
45
10
20
30
40
50
60
Time
33 % / 40 %
“To be safer, (re)move the safety”
Done
Today
Critical Chain
Current Longest Chain Detection
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 47: Progress example 2: 33 % progress on the longest chain / 40 % buffer used
Done
45
10
20
30
40
50
60
Time
33 % / 40 %
Project is still on track, but sits in the “orange” zone. You may need to take action.
“To be safer, (re)move the safety”
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 48: Progress example 3: 55 % progress on the longest chain / 65 % buffer used
Done
45
10
20
30
40
50
60
Time
55 % / 65 %
Relatively to much buffer is used. Measure are need to make sure the project can be delivered on time.
“To be safer, (re)move the safety”
Done
Done
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 49: Levers for achieving improvements Operations Management for (multi-)project operations
Introduction of Buffer Management with Dynamic Schedules Manage the Buffer
  Aggregate and (re-)move safety time
  Introduction of buffers at strategic positions to absorb uncertainty
Introduction of one single priority and feedback loop  Execute by single priority
  Track progress by Expected-Time-To-Complete (~ ETA)
  Synchronized Execution of Tasks
Introduction of Pipeline and Portfolio Management  Control the WIP
  Constraint based Work-in-Progress management
  Release management (staggering)
Introduction of Aggregation and (dynamic) “Late Binding”  Flexible Capacity

## Slide 50: Buffer Management addresses day-to-day resource conflicts (and prevents (bad) multi-tasking)
D2
D1
T1
How to solve the “resource conflict” for Mike?
D2
D1
Today
T1
D2
D1
T1
Today
T1
D2
D1
Execution sequence of the queue for Mike
The original plan for ONE System Engineer called “Mike”
Manage the Queue !
The actual situation Today
„In the Autopilot-Modus, Resource Managers , Task- and Project managers are supported by Operational Priorities for the synchronized execution of their projects”

## Slide 51: What is needed? Fast-Feedback Loop (ETTC)
Flawless handovers:
Ensure Delivery is complete
Be Ready-to-Start
  Good preparation
Continuous (frequent) update of the “Expected Time to Complete” for each active task (ETTC)
Notes: SHOW
We know now what we should not do but what do we need to do?

## Slide 52: “To do” List Sequenced by Priority – Focus on Getting Tasks Done
Notes:     1. Doorlooptijd van elke taak – er gaat meer dan 30 % verloren aan verstoringen, andere zaken
    2. Weniger Projekte geleichzeitig
    3. Stoppen met Teiltermine, focus op endtermine en een prioriteit
    4. Focus op fertig machen

## Slide 53: From Desynchronization to Synchronization (the value of single priorities)
30 Days
40 Days
Inefficient allocation
30 Days
20 Days
Efficient allocation
40 Days

## Slide 54: Manage Due Date delivery with CCPM Project and Cross-Project Optimisation (Portfolio or Program)
Per Project
Cross-Project (Program or Portfolio)
Red means “CRITICAL”. Risk of late delivery is high. Immediate “buffer recovery actions” need to be taken
Orange means CAUTION. There is a risk of late delivery. Recovery actions may need to be prepared.
Green means SAFE. The risk of a late delivery is small. No buffer recovery actions need to be taken or prepared.

## Slide 55: Levers for achieving improvements Operations Management for (multi-)project operations
Introduction of Buffer Management with Dynamic Schedules Manage the Buffer
  Aggregate and (re-)move safety time
  Introduction of buffers at strategic positions to absorb uncertainty
Introduction of one single priority and feedback loop  Execute by single priority
  Track progress by Expected-Time-To-Complete (~ ETA)
  Synchronized Execution of Tasks
Introduction of Pipeline and Portfolio Management  Control the WIP
  Constraint based Work-in-Progress management
  Release management (staggering)
Introduction of Aggregation and (dynamic) “Late Binding”  Flexible Capacity

## Slide 56: 4. Manage your portfolio with CCPM Global optimisation across projects

## Slide 58: The power of Buffer Management Simulations
Strategy | Setup | 1st project cmpl. | 1st project late | #Completed | #Late | hrs. overdue | #Red | %Yellow
Start date | 5% +MT | 21.14:00 | 26.15:00 | 21 | 15 | 3410 | 35 | 52%
Start date | 5% -MT | 20.12:00 | 22.09:00 | 29 | 15 | 2679 | 27 | 63%
Due date | 5% +MT | 21.9:00 | 21.14:00 | 20 | 15 | 2709 | 36 | 53%
Due date | 5% -MT | 16.14:00 | 36.11:00 | 41 | 12 | 846 | 14 | 83%
LYNX | 5% -MT | 17.9:00 | 141.12:00 | 50 | 1 | 2 | 0 | 97%
Buffer Management outperforms any other sequencing strategy!

## Slide 59: How to achieve improvements?
Aggregation and (dynamic) “Late Binding”

## Slide 60: Achieving more “Flow” and Resource Management Allocate work to team (or skill) first (not individuals)
Aggregation of resource requirements on „Skill“ or „Team“ Level
  Resources are “pooled” by „Skill“ or Team
  Specification of any “Task Resource Requirement” by “Skill”
Principle of (dynamic) “Late Binding”
  Keep your options open as long as possible (“rotation”)
  Prevent “Kopfmonopole”

## Slide 61: Scope LYNX TameFlow solution
Implementation of the ISA95 Skill / Resource and Aggregation model
  Skills
  Resources
  Profiles
Concept of „*Soft-Reservations“ for the implementation of:
  Principle of Aggregation and „Late Binding“
  The possibility of „Cross-Skill“ Management
  Control of reservations against „Profiles“
CCPM with optimal support of Resource Management
  Monitoring the Multi-Project Resource Load
  Stimulation of more flexibility by „Cross-skill“ training and assignments
  „Decision Support“ for optimizing of the capacity (Cross-Training, Hiring, Education)

## Slide 62: The “Late Binding“ solution within LYNX Specification of “Resource Requirements“
Implementation of the ISA95 Skill / Resource and Aggregation Model
  Skills
  Resources
  Profiles
Task Resource Requirements
Skill
Profiles
*Resource(s)
Projects and Tasks

## Slide 63: The “Late Binding“ solution within LYNX Specification of “Resource Requirements“
Resource Names
Implementation of the ISA95 Skill / Resource and Aggregation Model
  Skills
  Resources
  Profiles
Task Resource Requirements
Virtual Skill
# FTE
Projects and Tasks
Task Resource Requirements
Skill
Profiles
*Resource(s)
Projects and Tasks
Profiles

## Slide 64: LYNX basic structures for „Skills“ Available Capacity
ISA95
Resource Model
(„Normal“) Skill with Resource (Names):
  Available Capacity is the total of the individual availability of each resource, given ist calendar
  Considers also non-working periods
  There is a Skill / Resource Matrix
  „Cross-Skill“ Management for resources with multiple skills
Extended:
  Additional Skill / Resource Profiles
(„Virtual“) Skill (or Team):
  Available capacity expressed in #Full Time Equivalents (anonym)
  There are „only“ Skills and #FTE
Skill | # FTE
System Engineer | 5
Tester | 4
 |  | Profile |  | 
Skill | Name | Seniority | Product Group | Location
System Engineer | Michael | Senior | Electric/Road | Netherlands
 | Sven | Junior | Mountain/Road | Germany
 | Peter | Senior | Mounain | Netherlands
 | Karl | Medior | Road | Netherlands
 | Fabian | Senior | Electric | USA
Skill | Name | Calendar
System Engineer | Michael | Standard (5 days)
 | Sven | Standard (5 days)
 | Peter | Standard (5 days)
 | Karl | Standard (5 days)
 | Fabian | Standard (5 days)
Calendar
Standard (5 days)
Standard (5 days)
Standard (5 days)
4 days per week
50% Available
Name | Skill
Peter | Skill 1: Electrical Engineer
 | Skill 2: System Engineer
 | Skill 3: ……

## Slide 65: LYNX basic strucures for „Skills“ Available Capacity
Profile
Candidates
Skill
ISA95
Resource Model
Name | Calendar
*Steve | Standard (5 days)
*Tom | Standard (5 days)
*Richard | 4 days per week
*Peter | 50% Available
Profile |  | 
Seniority | Product Group | Location
Senior | Electric | Netherlands
Medior | Mountain | Germany
Junior | Road | USA
Skill | Resources
System Engineer | 4 Candidates

## Slide 66: Example: System Engineer needed for Task A Task Resource Requirements: *Soft-reservation funnel process (Matching-Resources)
*Baptiste
*Daniel
*Daniela
*Eric
*Heinrich
*Jochen
*Konstantin
*Markus
*Michael
*Oleg
*Olivier
*Werner
*Matthias
All
Product Group
Experience
*Baptiste
*Daniel
*Daniela
*Heinrich
*Konstantin
*Michael
Location
*Baptiste
*Daniela
*Konstantin
Confirmation of Daniela for TASK A
Daniela
Project Manager + Resource Manager + Portfolio Management
Soft-Assignment = *Name
*Baptiste
*Daniel
*Daniela
*Eric
*Heinrich
*Jochen
*Konstantin
*Markus
*Michael
*Olivier
*Werner
Germany
Electric Bikes
Senior

## Slide 67: Setting of Project / Task Resource Requirements Examples
START

## Slide 68: “Cross-Skill” Management and available capacity Assumes that Resource names are organised by skill and/or profiles
Peter has 40 hours per week available for either Skill
  However this does not mean that 2 * 40 = 80 hours are available
  The available 40 hours per week can only be used once
Examples:
  If a task needs 16 hours of Peter as „Electrical Engineer“
  This leaves only 24 hours available for assignment to either Skill:
    A maximum of 24 hours as Electrical Engineer
    Or a maximum of 24 hours as System Engineer
    Or any combination of both skill until 24 hours
„Cross-Skill“ applies to:
  The Skill Level
  Additional „Profile“ Level
Name | Availability | Skill
Peter | 5 days / 40 hrs per week | Skill 1: Electrical Engineer
 |  | Skill 2: System Engineer

## Slide 69: Example „Cross-Skill“ Management Mr. Albach has two skills or roles (Auftragzentrum and Projekt Manager)

## Slide 70: Not the complete answer… Example Case and Issues
Resource planning and management need to be included in the solution!

## Slide 71: Example Skill and Resources with Profiles
1
2
3
4
Seniority
Technology
Customer Exposure
Skill(s)
(SE)
n – Resources
(Daniel)
Profiles are examples
This model is following the ISA 95 Standard
Resource
(Daniel)
Location
Department
Languages
German
Dutch
English
Luxemburg
Engineering
Department
Daniel is a System Engineer mit Profile: BMW /.. + Radar/… + Senior
Daniel: Based in Luxemburg, works in the System Engineering Department and speaks German, Dutch and English
Resource Property Profile Daniel
A-dato Confidential
Skill Property Profile
BMW
Senior
Radar

## Slide 72: The Principle of (dynamic) „Late Binding“ and Capacity Flexibility Timing Skill Specification and Resource Confirmations
Project Planning Phase
Project Release Phase
Execution Phase
Skill Specifications
Resource Confirmations (names)
Confirmations preferably as late as possible
(when Tasks are Ready to Start !)

## Slide 73: Summary of the *Soft-Reservation Concept Application of the principles of Aggregation and “Late binding”
A *Soft-Reservation gives a Projectmanager the assurance, that the required capacity is reserved for his project.
A *Soft-Reservation means at the same time Flexibility for the Resource Manager, which allows him to consider alternatives until the „latest“ moment.
Also he has more accurate information about required capacity and profiles in the (near) future and when required.
Therefore he is able to pro-actively anticipate on these requirements.

## Slide 74: Demonstration

## Slide 75: Demonstration
LYNX Project and Portfolio Management
LYNX TameFlow:
  Example with Subtasks
  Example with Flow-Buffer Management
  Example with User Stories (and subtasks)

## Slide 76: Levers for achieving improvements Operations Management for (multi-)project operations
Introduction of Buffer Management with Dynamic Schedules Manage the Buffer
  Aggregate and (re-)move safety time
  Introduction of buffers at strategic positions to absorb uncertainty
Introduction of one single priority and feedback loop  Execute by single priority
  Track progress by Expected-Time-To-Complete (~ ETA)
  Synchronized Execution of Tasks
Introduction of Pipeline and Portfolio Management  Control the WIP
  Constraint based Work-in-Progress management
  Release management (staggering)
Introduction of Aggregation and (dynamic) “Late Binding”  Flexible Capacity

## Slide 77: How to achieve improvements? Introduction of Pipeline and Scenario planning
LYNX Release Wizard
LYNX Resource Load Graph
LYNX Pipeline and Scenario Planning

## Slide 78: Topics
“Constraint based” Portfolio Management
LYNX Release Wizard
LYNX Scenario Wizard
  LYNX Pipeline and Scenario planning

## Slide 79: Strategic Prioritization to control the Work-in-Progress and Sequence Projects
Complex systems typically have only one „Constraint“
5 Focussing steps
4 Levels of Constraints
„Staggering“ using a (virtual) drum e.g.:
  A critical phase in each project (integration)
  Specific Team(s)
Strategic priorities (ranking)
Results:
  Less WIP
  Reduction of Lead-time
  More output
§1 Identify
§2 Exploit
§3 Subordinate
§4 Eliviate
§5 Step 1 …
A phase
(integration)
A team
A specialist
The Market
Typical Constraint(s)
Project #1
#2
Project #4
PIPELINE
Project #3
Project # 5

## Slide 80: Identification of the “Constraint”
Current Load vs Capacity
10
100%
Load / Capacity
10
System Engineer
Skill D
Skill F
Skill G
100%
Load
System Engineer
Skill D
Skill F
Skill G
Target Load vs Capacity
Scenario Planning process

## Slide 81: Any system needs WIP control….
Cycle time (duration)
Reliability
OUTPUT

## Slide 82: LYNX Release Wizard Finding the optimal timeslot for each new project entering the “highway”
Virtual Drum(s)
Project D
Project B
Project A
Project C
Intelligent Access Control
(for new Projects)
Staggering
When green 1 car !
Notes: SHOW

## Slide 88: Pipeline Management & Resource Planning Key Questions to answer
Question 1: Are there any conflicts? If yes, where?
  Which of the skill(s) are likely to be the “constraint”?
  Which of these skill(s) is most used in the projects?
Question 2: How big is the problem actually?
  Without “Due-Date Tolerance”
  After using the “Due-Date Tolerance”
Question 3: Is it possible to expand the capacity, permanently or temporarily?
  Does this solve the problem?
  If not…
Question 4: What Pipeline sequence to implement?
  Which projects can be moved?
  What can be achieved?
Question 5: How to use available free capacity at other skill(s)?
  Which projects can be started, without impacting the “constraint” skills?
Starting point:
  “What-if” we want to deliver current and future projects in time?

## Slide 89: Scope
Ongoing work and projects (WIP)
Future work and projects
Resource Load
Skills
Resources
Availability
Inspired by TOC
Smart Planning & Scheduling

## Slide 90: Scenario planning Constraint Based
Project 2
Project 3
Project 1
Workpacage B
Workpackage A
Project 4
Project 2
Project 3
Project 1
Project 5
Project 6
Project 4
Questions:
What happens when resource or skill availability changes?
What happens when a project is delayed in order to free up resources?
What happens when a project is added to the pipeline?
What happens when a project is removed from the pipeline?

## Slide 91: “What if” you want to deliver current (and future) projects in time? (1)
Are there any capacity overloads?
  If yes, where? Which of the skill(s) are likely to be the “primary constraint”?
  Which of these skill(s) is most used in the projects?
  Is the "virtual drum" overloaded?
Is the current pipeline at risk?
  are there (too) many projects in the red zone of the fever chart?
  what is the trend?
Is there a problem? If yes, how big is the problem actually?
  How much delay can be expected, across all projects in the current portfolio pipeline?
  What is the expected "due-date" performance of your current portfolio pipeline?

## Slide 92: “What if” you want to deliver current (and future) projects in time? (2)
Is it possible to expand the capacity, permanently or temporarily?
  For which skill is this possible?
  Does this solve the problem?
Is resequencing of the pipeline required?
  Which projects have the highest business priority?
  Can projects with a lower business priority be postponed or (temporarily) put on hold?
  Does this free up capacity for the more important projects?
How to use available free capacity at other skill(s)?
  Which projects can be started, without impacting the “constraint” skills?

## Slide 93: Scenario n
Ongoing work and projects (WIP)
More future work and projects
Resource Load Analysis
Constraint(s) Detection
System engineer
Resources
Availability
Scenario n
Inspired by TOC
Smart Planning & Scheduling

## Slide 94: Being in control – the new standard
Make you projects flow

## Slide 95: Multi-Project Progress Chart Global optimisation across projects

## Slide 96: LYNX Portfolio view with configurable Fever chart

## Slide 97: A. Critical Penetrating Tasks Report Shows just the one critical task per project (Project Buffer or a Milestone buffer)

## Slide 98: Portfolio Status

## Slide 99: B. Project Status Buffer Status + Active Tasks + Notes
This report can be used by the Project Manager and Portfolio Manager to discuss the status of the projects.

## Slide 100: C. Flow Reports Cumulative Flow Diagram
WIP
Lead Time
Cycle Time
Backlog

## Slide 101: Multi-project Resource Management

## Slide 104: Flow diagram by skill

## Slide 105: Flow Trends KPI’s Queue Management

## Slide 106: C. Flow WIP Diagram by Skill Work-in-Progress Diagram

## Slide 107: Work-in-Progress Trend Line

## Slide 108: Summary

## Slide 109: Levers for achieving improvements Operations Management for (multi-)project operations
Introduction of Buffer Management with Dynamic Schedules Manage the Buffer
  Aggregate and (re-)move safety time
  Introduction of buffers at strategic positions to absorb uncertainty
Introduction of one single priority and feedback loop  Execute by single priority
  Track progress by Expected-Time-To-Complete (~ ETA)
  Synchronized Execution of Tasks
Introduction of Pipeline and Portfolio Management  Control the WIP
  Constraint based Work-in-Progress management
  Release management (staggering)
Introduction of Aggregation and (dynamic) “Late Binding”  Flexible Capacity

## Slide 110: LYNX and LYNX TameFlow
Projects with tasks
Portfolio / Multi-Project
Workpackages with Cards (subtasks, user-stories, cases)
Card
Multi-project resource management
(Skills, profiles, resources, teams, team members)

## Slide 111: LYNX Workflow Optimization – The Project “Factory”
Stakeholder
„Priority board“
teams
New projects
Layer 1
Multi-Project
Layer 2
Single Project
Layer 3
Workpackages Agile & Kanban
Pipeline & Scenario Planning
Release Wizard
Scenario Wizard
“Strategic Priorities”
Workpackages with Cards
Agile/Kanban Processes
e.g. Sub-tasks / Stories
Projects
CCPM or LFPM
Buffer Management
“Operational Priorities”
Project #1
#2
Project #4
PIPELINE
Project #3
Project # 5
Notes: 3 lagen model. – wat is dan nog een missing link?  kenniswerk. Agile and everything is good.

## Slide 112: LYNX and LYNX TameFlow Workflow optimisation with Resource Management
Optimal
Workflow
Optimal
Resourcing
Optimal
Results