## Slide 1: Get started with LYNX
Project Managers

## Slide 2: Contents
Registration and Login (5)
LYNX Overview (10)
Create your first project (21)
  Add Tasks (26)
  Add Dependencies (31)
  Add Skills and Resources (39)
  Add Task Managers (45)
  Apply CCPM Behavior (48)
Release your project and tasks for execution (56)
Configuration
Planning
Execution
Other:
  A few tips and tricks
  More information
https://www.a-dato.com/download-lynx/
DOWNLOAD LYNX
Visit the
LYNX HELP CENTER
https://support.a-dato.com/hc/en-us

## Slide 3: Visit the LYNX Help Center

## Slide 4: Search and Replace (CTRL F)

## Slide 5: Register as a new user OR Login by invitation with your (new) credentials received per email
Create a new account.
If you already received an invitation to join LYNX from another user (e.g. colleague, admin, workspace owner) your login credentials are provided in the invitation email.
If you are invited as a first-time user, LYNX will provide an initial password, which can be changed in MyProfile

## Slide 6: New User Registration
Do not forget to enter your initials.

## Slide 7: Login after registration with your email and your password

## Slide 8: My activities Your First Screen showing your activities / Select “ Configure”
If you are a new registered user, this screen is (still) empty.
If you are invited as a (new) user, for example in the role of Task Manager, your tasks may already be displayed here.
Select Configure as the next step.
If you are invited the name of an existing workspace is displayed here. For example “MyCompany” or “Training”

## Slide 9: Check or Update My Profile
Go to File  My profile
You can change your password here

## Slide 10: LYNX Overview

## Slide 11: LYNX Workflow Optimization – The Project “Factory”
Stakeholder
„Priority board“
teams
New projects
Layer 1
Multi-Project
Layer 2
Single Project
Layer 3
Workpackages Agile & Kanban
Pipeline & Scenario Planning
Release Wizard
Scenario Wizard
“Strategic Priorities”
Workpackages with Cards
Agile/Kanban Processes
e.g. Sub-tasks / Stories
Projects
CCPM
Buffer Management
“Operational Priorities”
Project #1
#2
Project #4
PIPELINE
Project #3
Project # 5
Notes: 3 lagen model. – wat is dan nog een missing link?  kenniswerk. Agile and everything is good.

## Slide 12: Layer 3 Integration LYNX TameFlow Task Board, including Flow Buffer Management

## Slide 13: Focus of this manual: Layer 2
Layer 2
Single Project
Create Projects
CCPM
Buffer Management
“Operational Priorities”

## Slide 14: Pooling of Contingency – Insurance Model Buffer Management
“To be safer, (re)move the safety”
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 15: Green 50 % progress on the longest chain / 15 % buffer used
Done
45
10
20
30
40
50
60
Time
50 % / 15 %
Project is on track. The risk that the project will be late is very low.
“To be safer, (re)move the safety”
Done
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 16: Red 55 % progress on the longest chain / 65 % buffer used
Done
45
10
20
30
40
50
60
Time
55 % / 65 %
Relatively to much buffer is used. Measure are need to make sure the project can be delivered on time.
“To be safer, (re)move the safety”
Done
Done
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 17: What can you do with Red, Orange and Green? Resolve day-to-day resource conflicts (and prevents (bad) multi-tasking)
D2
D1
T1
How to solve the “resource conflict” for Mike?
D2
D1
Today
T1
D2
D1
T1
Today
T1
D2
D1
Execution sequence of the queue for Mike
The original plan for ONE System Engineer called “Mike”
Manage the Queue !
The actual situation Today
„In the Autopilot-Modus, Resource Managers , Task- and Project managers are supported by Operational Priorities for the synchronized execution of their projects”

## Slide 18: What is needed? Fast-Feedback Loop (ETTC)
Flawless handovers:
Ensure Delivery is complete
Be Ready-to-Start
  Good preparation
Continuous (frequent) update of the “Expected Time to Complete” for each active task (ETTC)
Notes: SHOW
We know now what we should not do but what do we need to do?

## Slide 19: “To do” List Sequence from red to green
Notes:     1. Doorlooptijd van elke taak – er gaat meer dan 30 % verloren aan verstoringen, andere zaken
    2. Weniger Projekte geleichzeitig
    3. Stoppen met Teiltermine, focus op endtermine en een prioriteit
    4. Focus op fertig machen

## Slide 20: What can you do with Red, Orange and Green? Manage all projects together

## Slide 21: Create your First Project

## Slide 22: Add your first project
Select Project Portfolio in the Desktop Window (F5)
Select Add
Ensure the “Critical Chain Engine” is selected.
Select your preferences. In CCPM Just in Time is considered as “Best Practice.”
1
2
3
Add a Project ID and Project name (description)
Add an initial desired or requested end-date (due date)

## Slide 23: Your first project is listed in the Project Portfolio / Not started
TIP: Try right mouse-click on column headers for additional sorting and filtering
Filter applied to list of projects
Default filters to apply to list of projects:
Status “ Not Started”
Status “Released”
Show all
Show Templates
Your FIRST project (D1) has been created and is listed in the Project Portfolio, with status “ Not started”
Remove Filter
Double clicking opens the project
If you want to go back to or recover the default sorting and filtering

## Slide 24: The “Project Window” – Multiple Views and Windows
Task Grid
Gantt Chart
Task Properties
D1 Product Development Project Window
Confirms Task Property updates
Undo and Redo buttons
Multiple tabs
Also click in the Gantt area to confirm changes
Auto scale timebar

## Slide 25: Create the Project Plan
Add Tasks
Create the Project Network
  Add task dependencies (predecessors / successors)
Add (Virtual) Skills (and resources)
Convert the plan into a Critical Chain Plan

## Slide 26: Add Tasks

## Slide 27: Target Plan

## Slide 28: Add Tasks
Start here to create your first task.
Any new task gets a default duration of 1 day after giving the task a name. You can change the expected duration in the duration column.
Click in the Gantt Chart, to confirm your update! *
* Background of this process is the optimization of the performance and prevents that any (small) change triggers a re-calculation of the complete (large) project plan
Green Line = TODAY

## Slide 29: Add more tasks
Use the “down arrow” key on you key-board to quickly add new rows
Add a new task by pressing the +. Via the dropdown you can also add a task before (Ctrl Insert).
Press “Enter” or Click to confirm your changes
Delete a task with X
Tasks 2 – 6 are considered feeding chain tasks, not (yet) part of the “ Critical Chain”.
In this example “Feeding Chains” are positioned “ Just in Time,” offset against the Critical Chain (task 1).

## Slide 30: Save
Each tasks gets its own ID
Change Task duration here
Right click on header of the task list, to remove any unwanted filter or sorting.
Click on Auto scale for an adjusted timebar

## Slide 31: Add Dependencies

## Slide 32: Add Dependencies between tasks
Between task 1 and 2 there is a Finish-Start relation.
See also the CTRL Fast-Keys!
Button for adding dependencies between tasks. The default is a Finish-Start dependency (just click on button, without opening drop-down)
Task 1 and 2 are selected for adding a dependency (use SHIFT or CTRL to select two or more tasks)
Use the drop-down to see all options.
In CCPM typically only Finish Start is used.

## Slide 33: You can also select Tasks with your mouse in the Gantt Chart to add a dependency
Dependency will go from the task selected first to the next selected task(s)

## Slide 34: Add dependencies via the Edit Boxes Predecessor box and Successor box
The edit boxes are very useful especially in case of projects with many tasks.
Use this filter

## Slide 35: Deleting dependencies Via Task properties  Tab “Dependencies”
Delete Successor relationship between task # 3 and task #6.

## Slide 36: Add/update dependencies Select view  Data entry view

## Slide 37: Review result and statistics
Use the Auto scale timebar (F4), to scale your plan to fit in the Gantt window.
Task properties/Dependencies for task #6
Project statistics are displayed here.
Current length of the Critical Chain is 28 days

## Slide 38: Select “Critical Chain View”
Only tasks on the Critical Chain are displayed

## Slide 39: Add Skills & Resources

## Slide 40: Add skills (and resources)
A System Engineer will be added to the selected task(s)
Drag & Drop Skills to the selected tasks (1 or more)
Select the Skill/Resource/Task Manager Window
1.
2.

## Slide 41: Adding Skills via the Resource requirements column

## Slide 42: Review the resource load for your project
Resource Requirements for Task 2 are red shaded in the load graph

## Slide 43: Modify Task Estimated Time and Units % (optional)
You can modify the estimated time and unit percentage

## Slide 44: Review the resource load for your project (scenario Virtual Skills) Skills are “Virtual skills”
In case of “Virtual Skills” LYNX does not make a pre-selection and soft-allocates a resource name. Please refer to SLIDE 19

## Slide 45: Add Task Managers

## Slide 46: Invite multiple Task Managers involved to the TM List In a CCPM implementation typically a Task Manager is responsible for (daily) task updates
Invite a TM for task #1, only!
Add a TM to the TM List for the project
You can invite an existing user or invite a new user as a TM

## Slide 47: Add a Task Manager to task(s) Via the Task Manager column or via “Drag & Drop”
Add yourself as Task Manager to the first task
Mike Dempsey (current user) is added to task #1

## Slide 48: Apply CCPM Behavior

## Slide 49: Apply Critical Chain Behavior in 3 Steps
3
Decide about Task Time Reduction
You can keep or change the default percentages and confirm
Length of the Critical Chain has been shortened with 50 %
1
2

## Slide 50: Start a project from a template

## Slide 51: Start a project from a template Where to find available templates?

## Slide 52: Start a project from a template
1
2
3
Select Copy Project after filling in the Project ID & description

## Slide 53: Start a new project from a template
You can find your new project under “Not Started”

## Slide 54: Special Items
Summary Tasks
Milestone Buffers

## Slide 55: Special Items
Summary Tasks
Projects with multiple end-points:
  Milestone Buffer(s)
  Project Buffer

## Slide 56: Release your project
Create active tasks

## Slide 57: Release your project and its tasks
After Release LYNX has created two buffer controls (project buffer column and feeding buffer column)
The release of the project has resulted in an update and extension of the statistics
Select Project Properties
1
2
3

## Slide 58: Select My activities in the Desktop Window Update Ettc for your first task
1
2
3
The Task Manager can:
Assign and confirm resources for a task
Start a task by changing the status
Enter the Estimated Time to Complete (e.g. on a daily basis)
Opens the project plan

## Slide 59: A few tips and tricks

## Slide 60: Search and Replace (CTRL F)

## Slide 61: Mark Favorites

## Slide 62: A few tips and tricks
Copy a selection of tasks with CTRL C (Copy) and CTRL V (Paste)
Click in the Gantt Chart and then Use CTRL + Scroll to Zoom
Go to a “date line” and zoom in/out by moving the date line
FIND MORE TIPS AND TRICKS: https://support.a-dato.com/hc/en-us
Use right mouse click to filter / hide columns

## Slide 63: Continued
Right Click on a project row
All windows can be individually moved. You can use 2 screens side by side.
Right click on header of the project list, to remove any unwanted filter or sorting.

## Slide 64: Resolve Warning Messages Plan cannot be calculated due to planning logic violations
The messages can be viewed in the “Messages” tab
LYNX may not be able to recalculate the project due to a message.
In this example there is only 1 designer available. The planner has assigned 2 !

## Slide 65: Start adding “Notes”
1
Click on this icon to add a note
2
3
Select the type of note you want to create
Click the + icon to create a note

## Slide 66: Special Items
Buffer Recovery
Level of Effort Tasks
One Click “Click-through” from a task in the task-list, directly into the project
Down-stream / Upstream chain views based on any selected task in the schedule
Ability to share de-buffered plans with external parties or customers
Possibility to exclude tasks from task time reduction
Cross-skill Resource Management
Split Critical Chain tasks in case of multiple resource with different workload
Auto Complete Option
  intended for tasks with long and or fixed lead times only (such as shipping or purchasing tasks)
Display of “Last Progress Update”
  for tasks that are started, which provides fast feedback when the last ETTC update has taken place