## Sheet1
Meeting ALL Project Promises
|  | The Company has very high due-date performance without compromising on the content or on the budget. In the multi-project arena, very high due-date performance is defined as delivering well over 95% on (or before) the original promised due-dates, while in cases of late delivery the delay is much smaller than the prevailing delays in the industry. | The Company implements Critical Chain Project Management (CCPM) culture and procedures. |  |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A. | Reduce Bad Multi-tasking & WIP
| Flow is the number one consideration (the target is not how many projects the Company succeeds to start working on, rather it is how many projects are completed). |  | The Company properly controls the number of projects that are open at any given point in time |  |  | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Prioritizing and Freezing | The number of open projects is quickly reduced to be more inline with better flow and throughput. | The top manager in-charge of all projects, after consulting with his subordinates, determines the prioritization of projects and instructs to freeze (cease activities on) enough* of the lowest priority projects. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* “Enough”means: responsible for at least 25% of the load. The proper actions are taken to ensure full adherence to the freezing decision.
| Accelerate Project Completion | There is good (sufficient for accelerate project completion) assignment of resources to projects. | The optimal number of the various types of resources needed for each open project is determined. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The freed resources are used to prudently strengthen the open projects.
Proper manning decisions are also done for the frozen and to be released projects.
| Defrost Mechanism | Frozen projects are defrosted at a pace that maintains the reduced load | The company chooses integration (or part of it) as the VIRTUAL DRUM : | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The number of projects allowed in that section is restricted to be, at most, 75% of the current number.
When a project completes this integration a frozen project is defrosted.
The sequence of defrosting projects is according to the agreed projects prioritization.
| Releasing of new Projects | The timing for the release of each “leg”of a new project takes into account the lead-time of the leg. | When the time arrives to release new projects, steps B.Full Kitting and C.Critical Chain Planning & Buffering should be in place. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
At that stage, a system to release new projects using the CCPM concepts is ready.
B. | Full Kitting
| A project is rarely launched before its preparations are complete |  | The company uses the window of reduced load on resources that do the preparations to ensure that “full kit”practice will become the norm. | Not Started | Not Achieved | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Preparations according to priorities | Resources and project leaders are used to working on projects whose preparations are (almost) fully completed. | A Full-Kit manager is appointed. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The relevant resources are instructed to complete the preparation steps first for the running - not frozen - projects.
Then to complete the preparations for frozen projects.
Only when (most of) the above is done they are guided to work on the preparations for the new projects waiting to be released.
They always follow the projects priority.
| Defining Preparations | The permission (or even demand) to work on preparations does not violate the freeze and/or controlled release intentions. | The activities which should be titled preparations are officially defined as such. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The company takes the actions to ensure that resources (those conducting the preparations and project managers of frozen and unreleased projects) are guided and monitored to work only on the preparation activities as defined.
| Worried Clients | The threat of loosing projects due to a late start is alleviated. | The Company relentlessly completes all preparations (closes the gaps) on running and frozen projects. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: At that stage preparations are done on new projects and the exposure is drastically reduced. Once the Reliability offer is properly launched the above threat is completely removed.
C. | Critical Chain Planning & Buffering
| Flow is the number one consideration (it is not important to finish each task on time, it is essential to finish each project on time). |  | For all projects proper PERT networks are built (using templates where appropriate). | Not Started | Not Achieved | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The time estimates are cut in half and projects and feeding buffers are inserted according to Critical Chain Project Management (CCPM).
The projects are properly staggered.
Proper actions are taken to ensure that resources are aware that their estimates are regarded as just estimates - they will no longer be judged according to meeting their time estimates.
The resulting plan is used to properly release projects into operations.
The resulting planning ability is used to determine reliable and acceptable due-date commitments for new projects.
| Building Good Project Plans/PERTS | All projects about to be released have PROPERLY detailed PERTs. | All relevant projects (projects which are not to be soon completed and the projects to be released in the near horizon) are considered in order to determine the generic projects. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proper teams construct the templates per each generic project making sure that the resulting PERT will be PROPERLY detailed.
Per each relevant project enough uninterrupted time is devoted by the project-planning-team (the key people that constructed the template and the key project people), to PROPERLY modify the template to fit the specific project.
| Buidling Critical Chain Plans | The company uses Critical-Chain-PERTs that enable on-time, faster project completion. | A CCPM workshop is conducted for all people participating in the project-planning-teams. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
For each relevant project the project-planning-team continues by following the Critical-Chain process to turn the initial PERT into a Critical-Chain-PERT.
The templates are finalized.
| Staggering Project Portfolio | Projects are planned to ensure effective operation. | A proper team invests the time needed to emulate the VIRTUAL DRUM and to identify and correct the crucial data errors. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actions are taken to ensure that projects are released according to the plan (legs having different lead-times are released at correspondingly different dates).
Actions are taken to ensure that due dates for new projects are committed ONLY according to the STAGGERING mechanism (or top management’s decision to postpone a specific existing project).
D. | Managing Execution
| Projects are actively managed to ensure their successful, rapid completion. |  | Critical Chain Buffer Management is the ONLY system used to provide priorities. | Not Started | Not Achieved | FALSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Priority reports are provided in different forms to different management functions.
Mechanisms are set to enable proper usage of the priority information.
| Task Completion Reporting | The required data is always adequately available. | Proper explanation is given to all task managers: what is required from them to report on a daily basis, how this information is going to be used and that they will, at last, be able to obey ONLY the formal priority list. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The company launches the daily reporting (by task managers - not by the resources) procedure and relentlessly enforces it.
| Task Managers role in managing execution | Tasks are executed according to their priorities. Preparations and corrective actions are taken in due time. | Following the priorities, task managers assign the optimal number of resources to tasks. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task managers review daily two lists of tasks (open and incoming) and according to the up-to-date priorities make sure tasks are effectively progressing.
| Project Managers role in managing execution | Project managers are driving a “project buffer recovery" process for cross departmental actions and exceptions not handled by task management. | Project managers review daily the list of tasks penetrating the most into the project buffer and check if recovery actions are taken or required to ensure that the project is effectively progressing. In extreme cases the project’s Critical Chain PERT (and even the template) are updated. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Top Management role in managing execution | Top management is well informed and in full control. | Top management reviews periodically (every two weeks) the projects’status. For projects whose progress is not satisfactory, the recovery actions are examined. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Virtual Drum adjustments | The Company’s rate of completing projects is in accordance with the Company’s changing capabilities. | The Company constantly monitors the number of projects in and before the chosen integration and periodically adjusts the rate of the Virtual-Drum in accordance. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E. | Mitigating Clients Disruptions
| The Company has very high due-date performance even in cases where client inputs are required and/or specification changes occur. |  | The client professionals are exposed to the CCPM project network and the logic of its buffers. | Not Started | Not Achieved | TRUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The Company people who interact with the client are professional at communicating the impact the client actions have on the completion of their project and the resulting damage.
The mechanism is in place to adjust due-date commitments when applicable.
F. | Managing Sub-Contractors or Contracted Sub-Projects
| The Company has very high due-date performance even in cases where sub-projects are contracted. |  | The Company provides on-going focus to the sub-contractors. | Not Started | Not Achieved
When appropriate, the Company is careful to provide the right incentives for satisfactory on-time performance to its sub-contractors.