## TameFlow Timespan
Automated Sizing and Remaining Duration from Cards (Timebased)
|  | Configuration |  |  |  | Explanation |  |  |  | Skill assignment and WP Duration |  |  | When a WP is started |  |  |  | Progress measurement
| Workpackage Content | Size identifier | Default WP Duration and Size | UoM Configuration | Card Type Fields | Size Monitoring (warning) | Automation | Conditions | Works with: | Skill Assignment | Default Output | Control of WP Project Duration | Scope Buffer | Increase WP Duration? | Board Cards Sequence | Progress measurement | Burn down | WP Remaining duration (Ettc)
T-1 | Cards with Original Estimate only | Size "Unit-of-Measure" (Timespan = hours) | Per Size UoM Conversion Rate | Estimate as Timespan with a Size "Unit of Measure" | Estimate (holds the original estimate) | Sum of Card Sizes (Estimate) is compared with estimated WP Size set. Warning when Sum is larger than Estimated WP Size | N.A. |  | Default Board Tameflow Kanban Board | Team Skill | # Hours per week per Size UoM (or day or month) | Size/(Skill Output p/w *Unit%) | If sum of Card Sizes (Org.Est.) is less then estimated WP Size set | If sum of Card Sizes (Org.Est.) is larger then estimated WP Size set | Only when a WP is started cards are published on the board. Top-to-Bottom sequence is determined by the user in the cards view | Automated from Burndown | By sum of Card Sizes (Org. Est.) with status closed | See left
| e.g. Subtask, work-item, etc. | e.g. Output, Productivity | Output = 40 hrs per week | e.g. Output | Select Estimate and property type: "Property holds original estimate of the card" | WP size is estimated as 80 hours, sum of card sizes (from cards) is 50. There is room for more cards for in total 30 hours more. |  |  |  | Engineering Team | e.g. Output = 40 hours p/w | 80 hours/(40*200%) = 80h@80h p/w = 5 days | If WP size is 80 hrs and value "from cards" is 50 hrs, a scope buffer of 30 hrs will be remain | If WP size is 80 hours, but actual "from cards" is > 80 hours. |  |  | If WP Size was 80 hours, and 60 hours have been completed, 25 % of the duration remain. | See left
T-2 | Cards with Org.Estimate/Ettc | See above | See above | Estimate as Timespan with "output" Ettc as Timespan | Estimate (holds the original estimate) Ettc (holds estimated time to complete) | See above |  |  | Default Board Tameflow Kanban Board | See above | See above | See above | See above | See above | See above | Automated from Ettc | See above | By sum of Cards Ettc, as calculated in "Open Cards", divided by output
T-3 | Cards with Org.Estimate/Ettc/Buffer M. | See above | See above | Estimate as Timespan with "output" Ettc as Timespan Due date as DateTime | Estimate (holds the original estimate) Ettc (holds estimated time to complete) Due date | See above | 1. Auto-update Original Estimate and Ettc from Card Type Buffer Management | Configuraton of minimal 1 Stream/Board via TameFlow Kanban | Tameflow Kanban Board only | See above | See above | See above | See above | See above | See above. Top-to-Bottom sequence based on buffer status | Automated from Ettc | See above | See above
T-4 | Cards with Org.Estimate/Ettc/TimeSp. (Buffer M. is optional) | See above | See above | Estimate as Timespan with "output" Ettc as Timespan Time Spent as Timespan | Estimate (holds the original estimate) Ettc (holds estimated time to complete) Time Spent (holds the actual time spent) | See above | See 1. above. 2. Time Spent decreases Ettc of a Card automatically with Time a card spends in a WIP column |  | Default Board Tameflow Kanban Board | See above | See above | See above | See above | See above | See above | Automated from Ettc, where Ettc is reduced with Time Spent automatically. | See above | By sum of Cards Ettc minus Time Spent, as calculated in "Open Cards", divided by output
T-5 | Cards with Org.Estimate/TimeSp./Buffer M. | See above | See above | Estimate as Timespan with "output" Due date as DateTime Time Spent as Timespan | Estimate (holds the original estimate) Due date Time Spent (holds the actual time spent) | See above | See 1. above. 2. Time Spent decreases Ettc of a Card automatically with Time a card spends in a WIP column | Configuraton of minimal 1 Stream/Board via TameFlow Kanban | Tameflow Kanban Board only | See above | See above | See above | See above | See above | See above. Top-to-Bottom sequence based on buffer status | Automated from Estimate, where Estimate is reduced with Time Spent automatically. | See above | By sum of Cards Estimate minus Time Spent, as calculated in "Open Cards", divided by output
User determined progress (Ettc)
|  | Configuration |  |  |  | Explanation |  |  |  | Skill assignment and WP Duration |  |  | When a WP is started |  |  |  | Progress measurement
| Workpackage Content | Size identifier | Default WP Duration and Size | UoM Configuration | Card Type Fields | Size Monitoring (warning) | Automation | Conditions | Works with: | Skill Assignment | Default Output | Control of WP Project Duration | Scope Buffer | Increase WP Duration? | Board Cards Sequence | Progress measurement | Burn down | WP Remaining duration (Ettc)
TS1 | Cards with Org.Estimate/Manual Ettc | Size "Unit-of-Measure" (Timespan = hours) | Estimated Time in the WP Resource Requirement box | Estimate as Timespan with "output" Ettc as Timespan | Estimate (holds the original estimate) Ettc (holds estimated time to complete) | Sum of Card Sizes (Estimate) is compared with estimated WP Size set. Warning when Sum is larger than Estimated WP Size | N.A. | N.A | Default Board Tameflow Kanban Board | Standard Skill (Normal or Virtual) No assignment | N.A. | Estimated Time / Standard | N.A. | Manual | Only when a WP is started cards are published on the board. Top-to-Bottom sequence is determined by the user in the cards view | Ettc set by user | By sum of Card Sizes (Org. Est.) with status closed | Ettc set by user
TS2 | Any "Team scenario" (T-1 until T-5) 1 Team Skill + N standard skills | See T-1 until T-5 | See T-1 until T-5 | See T-1 until T-5 | See T-1 until T-5 | See above See T-1 until T-5 | See T-1 until T-5 | See T-1 until T-5 | See T-1 until T-5 | Team Skill Standard Skills (Normal or Virtual) No assignment | See T-1 until T-5 | Per Team scenario T1 unitl T5 OR Estimated Time / Standard The longest duration wins | See T-1 until T-5 | Per T-1 until T-5 OR Manual for standard skills | See T-1 until T-5 | Per T-1 until T-5 Ettc set by user for Standard Skills The longest Ettc wins | By sum of Card Sizes (Org. Est.) with status closed | Per T-1 until T-5 Ettc set by user for Standard Skills The longest Ettc wins

## TameFlow Units
Automated Sizing and Remaining Duration from Cards (Abstract Units Based)
|  | Configuration |  |  |  | Explanation |  |  |  | Skill assignment and WP Duration |  |  | When a WP is started |  |  |  | Progress measurement
| Workpackage Content | Size identifier | Default WP Duration and Size | UoM Configuration | Card Type Fields | Size Monitoring (warning) | Automation | Conditions | Works with: | Skill Assignment | Default Output | Control of WP Project Duration | Scope Buffer | Increase WP Duration? | Board Cards Sequence | Progress measurement | Burn down | WP Remaining duration (Ettc)
U-1 | Cards with Units(points) only | Size "Unit-of-Measure" (Double = units) | Per Size UoM Conversion Rate | "Abstract" Units (points) as double with a Size "Unit of Measure" | Points | Sum of Card Sizes (Points) is compared with estimated WP Size set. Warning when Sum is larger than Estimated WP Size | N.A. |  | Default Board Tameflow Kanban Board | Team Skill | # Points per week per Size UoM (or day or month) | Size/(Skill Output p/w *Unit%) | If sum of Card Sizes (Points) is less then estimated WP Size set | If sum of Card Sizes (Points) is larger then estimated WP Size set | Only when a WP is started cards are published on the board. Top-to-Bottom sequence is determined by the user in the cards view | Automated from Burndown | By sum of Card Sizes (Points) with status closed | See left
| Features, User Stories, | e.g. Throughput, Velocity | Throughput = 20 points per week | e.g. Throughput |  | WP size is estimated as 40 points, sum of card sizes (from cards) is 25 points. There is room for more cards for in total 15 points. |  |  |  | Software Team | e.g. Throughput = 30 points p/w | 40 points/(30*200%) = 40 points@60 points p/w = 2,5 days | If WP size is 40 points and value "from cards" is 30 points, a scope buffer of 10 points will remain | If WP size is 40 points hours, but actual "from cards" is >40 points. |  |  | If WP Size was 40 points, and 30 points have been completed, 25 % of the duration remain. | See left
U-2 | Cards with Units(Points)/Ettc | See above | See above | "Abstract" Units (points) as double Ettc as Timespan | Points Ettc (holds estimated time to complete) | See above | When auto-update is selected, Ettc value is auto-updated from Skill output tab with points to hours conversion rate for selected Size UoM (Throughput) |  | Default Board Tameflow Kanban Board | See above | # Points per week per Size UoM (or day or month), with Team Production conversion | See above | See above | See above | See above | Automated from Ettc | See above | By sum of Cards Ettc, as calculated in "Open Cards", divided by output + still available scope buffer
U3.1 | Cards with Points/Org.Est.(1)/Ettc | See above | See above | "Abstract" Units (points) as double Ettc as Timespan Estimate as Timespan | Points Ettc (holds estimated time to complete) Estimate (property has no special meaning) | See above | When auto-update is selected, Ettc value and Original Estimate is auto-updated from Skill output tab with points to hours conversion rate for selected Size UoM (Throughput) |  | Default Board Tameflow Kanban Board | See above | See above | See above | See above | See above | See above | Automated from Ettc | See above | See above
U-3.2 | Cards with Points/Org.Est.(2)/Ettc | See above | See above | "Abstract" Units (points) as double Ettc as Timespan Estimate as Timespan | Points Ettc (holds estimated time to complete) Estimate (holds the original estimate) | No Size Warning! | When auto-update is selected, Ettc value and Original Estimate is auto-updated from Skill output tab with points to hours conversion rate for selected Size UoM (Throughput) |  | Default Board Tameflow Kanban Board | See above | See above | See above | No scope buffer Size and Duration WP is calculated from "Open Cards" value, excluding scope buffer. | See above | See above | Automated from Ettc | See above | By sum of Cards Ettc, as calculated in "Open Cards", divided by output
U-4 | Cards with Points/Org.Est./Ettc/Buffer M. | See above | See above | "Abstract" Units (points) as double Ettc as Timespan Estimate as Timespan Due date as DateTime | Points Ettc (holds estimated time to complete) Estimate (property has no special meaning) Due date | See above | When auto-update is selected, Original Estimate (and Ettc) is set from Card Size in Buffer Management tab | Configuraton of minimal 1 Stream/Board via TameFlow Kanban | Tameflow Kanban Board | See above | See above | See above | See scenario U-1 | See above | See above. Top-to-Bottom sequence based on buffer status | Automated from Ettc | See above | By sum of Cards Ettc, as calculated in "Open Cards", divided by output + still available scope buffer
U-5 | Cards with Points/Org.Est./Ettc/TimeSp./Buffer M. | See above | See above | "Abstract" Units (points) as double Ettc as Timespan Estimate as Timespan Due date as DateTime Time Spent as Timespan | Points Ettc (holds estimated time to complete) Estimate (property has no special meaning) Due date Time Spent (holds the actual time spent) | See above | 1. When auto-update is selected, Original Estimate (and Ettc) is set from Card Size in Buffer Management tab 2. Time Spent decreases Ettc of a Card automatically with Time a card spends in a WIP column | Configuraton of minimal 1 Stream/Board via TameFlow Kanban | Tameflow Kanban Board | See above | See above | See above | See scenario U-1 | See above | See above. Top-to-Bottom sequence based on buffer status | Automated from Ettc, where Ettc is reduced with Time Spent automatically. | See above | By sum of Cards Ettc minus Time Spent, as calculated in "Open Cards", divided by output + available scope buffer
U-6 | Cards with Points/Org.Est./TimeSp./Buffer M. | See above | See above | "Abstract" Units (points) as double Estimate as Timespan Due date as DateTime Time Spent as Timespan | Points Estimate (property has no special meaning) Due date Time Spent (holds the actual time spent) | See above | 1. When auto-update is selected, Original Estimate (and Ettc) is set from Card Size in Buffer Management tab 2. Time Spent decreases Ettc of a Card automatically with Time a card spends in a WIP column | Configuraton of minimal 1 Stream/Board via TameFlow Kanban | Tameflow Kanban Board | See above | See above | See above | See scenario U-1 | See above | See above. Top-to-Bottom sequence based on buffer status | Automated fromEstimate, where Estimate is reduced with Time Spent automatically. | See above | By sum of Cards Estimate minus Time Spent, as calculated in "Open Cards", divided by output + available scope buffer
User determined progress (Ettc)
|  | Configuration |  |  |  | Explanation |  |  |  | Skill assignment and WP Duration |  |  | When a WP is started |  |  |  | Progress measurement
| Workpackage Content | Size identifier | Default WP Duration and Size | UoM Configuration | Card Type Fields | Size Monitoring (warning) | Automation | Conditions | Works with: | Skill Assignment | Default Output | Control of WP Project Duration | Scope Buffer | Increase WP Duration? | Board Cards Sequence | Progress measurement | Burn down | WP Remaining duration (Ettc)
US1 | Cards with Units(Points)/Manual Ettc | Size "Unit-of-Measure" (Double = units) | Per Size UoM Conversion Rate | "Abstract" Units (points) as double with a Size "Unit of Measure" | Points | Sum of Card Sizes (Points) is compared with estimated WP Size set. Warning when Sum is larger than Estimated WP Size | N.A. |  | Default Board Tameflow Kanban Board | Normal or Virtual Skill No assignment | N.A. | Estimated Time / Standard updated by Task Manager or Resource | N.A. | Manual | Only when a WP is started cards are published on the board. Top-to-Bottom sequence is determined by the user in the cards view | Ettc set by user | By sum of Card Sizes (Points) with status closed | Ettc set by user
US2 | Any "Team scenario" (U-1 until U-5) 1 Team Skill + N standard skills | See U-1 until U-5 | See U-1 until U-5 | See U-1 until U-5 | See U-1 until U-5 | See above See U-1 until U-5 | See U-1 until U-5 | See U-1 until U-5 | See U-1 until U-5 | Team Skill Standard Skills (Normal or Virtual) No assignment | See U-1 until U-5 | Per Team scenario U-1 unitl U-5 OR Estimated Time / Standard The longest duration wins | See U-1 until U-5 | Per U-1 until U-5 OR Manual for standard skills | See U-1 until U-5 | Per U-1 until U-5 Ettc set by user for Standard Skills The longest Ettc wins | By sum of Card Sizes (Points) with status closed | Per U-1 until U-5 Ettc set by user for Standard Skills The longest Ettc wins