## Slide 1: LYNX Project and Portfolio Management Critical Chain Project Management
LYNX Training - Introduction

## Slide 2: Scope
Plan the Work
Work the Plan
Communicate
Introduction
Project
Tasks
Workpackages
Cards
Task Management
Cards Management
Kanban Board
What is
LYNX about?
Progress
Reports
Export

## Slide 3: Collaboration and Teamwork Working together at the same time in the same project(s)
Projects, tasks, sub-tasks, cards
Resource manager
Team manager
Task manager
Skill/ Resource
Project manager
Portfolio manager
Team member
Just “invite” others in one “click”
“Timing is everything”
There is only 1 moment you can be on time!
If you are not there you are either too early or too late.
Johan Cruijff
A-dato Confidential
External partner

## Slide 4: Why LYNX? LYNX brings everything together..
Projects with stages, phases, tasks, workpackages
with cards
Portfolio / Multi Project
Scenario Planning & Simulation
Taskboards with Cards e.g. subtasks, user-stories
Card
Multi-Skill Resource Management
Skills, profiles, resources, teams, team members
Portfolio manager
Project manager
Resource manager
Team manager
Task manager
Team member
Resource

## Slide 5: Why LYNX? Embedding Agile/Kanban way of working into projects
The TameFlow Approach
Through LYNX TameFlow, Agile and Kanban workflows are integrated, bringing Agile CCPM to life.
Project manager
Team member
Level 1
Level 2
Level 2
Task manager

## Slide 6: Why LYNX? Enabling a different approach offering ingredients to improve…..
Overload
Multi-tasking
Task Interruptions
Cherry picking
Early starts
De-synchronisation
Batching
Parkinson’s law
Student syndrome
Local safeties
Kopfmonopole
Global priorities
WIP Control
Roadrunner
  Single tasking
Single-touching
  Global buffers
Late binding
Full-kit
Single-piece flow
  Late binding
Tomorrow
A different approach
Today
Less pressure and stress
Easier collaboration
More reliable projects
Better timing, more flow
More transparency
Win (back) capacity
Finish projects faster
…..
Improvement Potential...
Symptoms
New Reality

## Slide 7: LYNX Role Based Training
LYNX for Project Managers
LYNX for Portfolio Managers (multi-project)
  Master Schedulers
  Release Managers
LYNX for Resource Managers
LYNX for Task Managers
LYNX TameFlow
  Team Managers
  Teams
  Team members
Full Users
Light Users
Team Users

## Slide 8: Summary Customer Overview
Fields of application
  Design and Engineering
  Building and Construction
  Service and Maintenance
  Organisation
Global footprint
  Currently over 100 customers, across all continents
  From small to very large implementations (with over 400 users and hundreds of projects)

## Slide 9: Diamond Aircraft Industries

## Slide 10: Diamond Air Experiences and improvements
What has improved and is better?
  Self-organizing teams across the companies
  Teamwork & mutual support across projects.
  Continuous improvement & innovation
  Burnout rate zero, stable operations
  Transparency (real-time information) is up
Deblocking Board for Project Managers

## Slide 11: ORTEC

## Slide 12: Before we start…
Login and Workspaces

## Slide 13: Visit the LYNX Help Center

## Slide 14: Login with your (new) credentials you received per email
If you already received an invitation to join LYNX from another user (e.g. colleague, admin, workspace owner) your login credentials are provided in the invitation email.
If you are invited as a first-time user, LYNX will provide an initial password, which can be changed in MyProfile

## Slide 15: Setting up your account in Lynx
There are many ways to Rome, I tell you the most convenient for now:
Opening lynx
Setting up your personal data in “Profile”

## Slide 16: New User Registration
Do not forget to enter your initials.

## Slide 17: Login after registration with your email and your password

## Slide 18: Select “My profile”
This screen this screen may still be empty (as long as no tasks are assigned to you)
The name of you “Space” is displayed here.

## Slide 19: Check (change) your “Space”
The name of you “Space” is displayed here.

## Slide 20: Get started with LYNX
LYNX for Project Managers

## Slide 21: LYNX Role Based Training
LYNX for Project Managers
LYNX for Portfolio Managers (multi-project)
  Master Schedulers
  Release Managers
LYNX for Resource Managers
LYNX for Task Managers
LYNX TameFlow
  Team Managers
  Teams
  Team members
Full Users
Light Users
Team Users

## Slide 22: Contents
A different approach
Philosophy behind LYNX
Create your first project (21)
  Add Tasks (26)
  Add Dependencies (31)
  Add Skills and Resources (39)
  Add Task Managers (45)
  Apply CCPM Behavior (48)
Release your project and tasks for execution (56)
Introduction
Planning
Execution
Other:
  A few tips and tricks
  More information
https://www.a-dato.com/download-lynx/
DOWNLOAD LYNX
Visit the
LYNX HELP CENTER
https://support.a-dato.com/hc/en-us

## Slide 23: Project Control – Think Different

## Slide 24: Theory: Project management principles
Theory
If all tasks finish in time, the project finishes on time
A delay on the critical path is a delay on the project
Dedicated team does the work

## Slide 25: Practice: Most projects are late and over budget!
Practice
Tasks run late even if you gave yourself extra time. In the end the project is late
One of your team members is working on another assignment
Murphey does exist and things derail
………..
Room for Improvement….

## Slide 26: Let’s take a different approach…

## Slide 27: Philosophy (behind Lynx)
Projects consist of people!
Thus, when managing projects, it is about people
(and processes).

## Slide 28: Task Durations (within Projects)
100 %
Wait
Work
Work
Typical
“Flow Ratio”
Work
Work
Work
Work
Wait
Typical task Execution Pattern
Work
Task
10 - 20 %
Notes: Vaak niet boeven 20 % - EERDER ROND DE 5
Zin is krom.  om echtt te verbeteren kan je veel nbeter richten op verminderen van de wachttijden

## Slide 29: Where to start improving? “Low” hanging fruit
Wait
Work
Most jobs are not slow, but typically just have to wait a lot.
Notes: Overlay met euro tekens, waar zet je geld op in?  groen kost heel veel.

## Slide 30: Today: What makes people (and organisations) unhappy?
Undesired
Too many things going on = mental pressure
Delays and waiting time
Many unfinished tasks, more Work-in-Progress
Task Interruptions
Favorite tasks first
Working on non-critical work first
Efficient but not effective
Every person adds private buffer – long leadtimes
Low Flow Ratio
Budget time  Actual time
Last minute rushing, forget stuff
A guaranteed “bottleneck”
Impact
Overload
Multi-tasking
Task Interruptions
Too early starts
Cherry picking
De-synchronisation
Batching
Local safeties / Padding
Spreading resources thin
Parkinson’s law
Student syndrome
“Kopfmonopole”

## Slide 31: Tomorrow: What makes people (and organisations) happy?
Desired
“Constraint” thinking  Work on less than X things at the time
Inverse of multi-tasking
Less interruptions = higher flow %
Everything is prepared to finish in one go (mise en place)
Prevents loud-mouth-management
The show CAN go on
Effective instead of efficient
Team focus on project “constraint”
Good enough estimates will do
No handover delays
Impact workfloor directly visible on strategic level
Flexibility and high flow ratio
Impact
WIP Control
Single tasking
Single-touching
Full-kit
Objective priorities
Synchronisation
Single-piece flow
Global buffers
Aggregation
Relay race
  Vertical Integration
  Late binding

## Slide 32: How to get there?
Desired
Different way of planning
Undesired
Different way of working
Overload
Multi-tasking
Task Interruptions
Too early starts
Cherry picking
De-synchronisation
Batching
Local safeties
Padding
Parkinson’s law
Student syndrome
Kopfmonopole
WIP Control
Single tasking
Single-touching
Full-kit
Objective priorities
Synchronisation
Single-piece flow
Global buffers
Aggregation
Roadrunner
  Vertical Integration
  Late binding

## Slide 33: Any system needs WIP control….
Cycle time (duration)
Reliability
OUTPUT

## Slide 34: A different approach… Critical Chain (Multi-)Project Management: Key Ingredients
Buffer
50%
Execute by Single Priority
Traffic light = 1 Operational Priority for everybody (across projects)
Buffer Management
+ Critical Chain
Manage across projects
(Control the WIP)
Heatmap or Feverchart

## Slide 35: CCPM: Theory of Constraints What do we mean with a “Critical Chain”?
The “critical path” (longest path) is the “bottleneck” in a project because it determines the total duration of the project………
Or isn’t it……?
The capacity of the “bottleneck” determines the maximum output that can be achieved
A
A
B
C
D
8
5
2
1
5
15

## Slide 36: CCPM: Critical Resources
Question:
Who are the critical resources or critical departments within your company?
What is impact of their availability on your project or other projects?

## Slide 37: CCPM: Critical Resources  impact on your project.. Ability to identify “Invisible dependencies”
A
A
B
C
D
8
5
2
1
5
Critical Path = 14
19
A
A
B
C
D
8
5
2
1
5
15
Critical Chain = 19
Task B is not Critical !

## Slide 38: Levers for improvement! Operations Management for (multi-)project operations
Introduction of Buffer Management with Dynamic Schedules Manage the Buffer
  Aggregate and (re-)move safety time
  Critical Longest Chain Scheduling
Introduction of one single priority and feedback loop  Execute by single priority
  Synchronized Execution of Tasks
  Track progress by Expected-Time-To-Complete (~ ETA)
Introduction of Pipeline and Portfolio Management  Control the WIP
  Constraint based Work-in-Progress management
  Flow Control with Release management (staggering)
Introduction of Aggregation and (dynamic) “Late Binding”
  By skill(group)  Flexible Capacity

## Slide 39: Improving with LYNX..
Stakeholder
„Priority board“
teams
New projects
Layer 1
Multi-Project
Layer 2
Single Project
Layer 3
Workpackages Agile & Kanban
Pipeline & Scenario Planning
Release Wizard
Scenario Wizard
“Strategic Priorities”
Workpackages with Cards
Agile/Kanban Processes
e.g. Sub-tasks / Stories
Projects
CCPM Engine
Buffer Management
“Operational Priorities”
Project #1
#2
Project #4
PIPELINE
Project #3
Project # 5
Notes: 3 lagen model. – wat is dan nog een missing link?  kenniswerk. Agile and everything is good.

## Slide 40: Layer 3: LYNX TameFlow Task Board, including Flow Buffer Management

## Slide 41: Focus of this Training: Layer 2
Layer 2
Single Project
Create Projects
CCPM
Buffer Management
“Operational Priorities”

## Slide 42: Introduction of Buffer Management
What can you do with Red, Orange and Green?

## Slide 43: A Standard Plan
CRITICAL CHAIN / PATH = 60
10
20
30
40
50
60
Time
Achievable
Contingency
Psychological effects of the standard plan:
Safe estimates (or overambitions)
Student Syndrome
Parkinson's law
Padding
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 44: A Buffered Plan (1)
45
10
20
30
40
50
60
Time
Achievable
Contingency
2/3
1/3
Pooling of Contingency Insurance Model
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 45: A Buffered Plan (2)
60
10
20
30
40
50
60
Time
Achievable
Contingency
2/3
1/3
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 46: Pooling of Contingency – Insurance Model Buffer Management
“To be safer, (re)move the safety”
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 47: Green 50 % progress on the longest chain / 15 % buffer used
Done
45
10
20
30
40
50
60
Time
50 % / 15 %
Project is on track. The risk that the project will be late is very low.
“To be safer, (re)move the safety”
Done
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 48: Red 55 % progress on the longest chain / 65 % buffer used
Done
45
10
20
30
40
50
60
Time
55 % / 65 %
Relatively to much buffer is used. Measure are need to make sure the project can be delivered on time.
“To be safer, (re)move the safety”
Done
Done
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 49: What can you do with Red, Orange and Green? CCPM: Project Trend Line
Fever Chart

## Slide 50: What can you do with Red, Orange and Green? Resolve day-to-day resource conflicts (and prevents (bad) multi-tasking)
D2
D1
T1
How to solve the “resource conflict” for Mike?
D2
D1
Today
T1
D2
D1
T1
Today
T1
D2
D1
Execution sequence of the queue for Mike
The perfect original plan for ONE System Engineer called “Mike”
Manage the Queue !
The actual situation Today
„In the Autopilot-Modus, Resource Managers , Task- and Project managers are supported by Operational Priorities for the synchronized execution of their projects”

## Slide 51: “To do” List: My activities Sequence from red to green
Notes:     1. Doorlooptijd van elke taak – er gaat meer dan 30 % verloren aan verstoringen, andere zaken
    2. Weniger Projekte geleichzeitig
    3. Stoppen met Teiltermine, focus op endtermine en een prioriteit
    4. Focus op fertig machen

## Slide 52: What can you do with Red, Orange and Green? Manage all projects together

## Slide 53: What is needed? Fast-Feedback Loop (ETTC)
Flawless handovers:
Ensure Delivery is complete
Be Ready-to-Start
  Good preparation
Continuous (frequent) update of the “Expected Time to Complete” for each active task (ETTC)
Notes: SHOW
We know now what we should not do but what do we need to do?

## Slide 54: How to achieve improvements?
Aggregation and (dynamic) “Late Binding”

## Slide 55: Achieving more “Flow” and Resource Management Allocate work to team (or skill) first (not individuals)
Aggregation of resource requirements on „Skill(group)“ or „Team“ Level
  Resources are “pooled” by „Skill“ or Team
  Specification of any “Task Resource Requirement” by “Skill”
Principle of (dynamic) “Late Binding”
  Keep your options open as long as possible (“rotation”)
  Prevent “Kopfmonopole”

## Slide 56: The “Late Binding“ solution within LYNX Specification of “Resource Requirements“
Resource Names
Implementation of the ISA95 Skill / Resource and Aggregation Model
  Skills
  Resources
  Profile Properties
Task Resource Requirements
Virtual Skill
# FTE
Projects and Tasks
Task Resource Requirements
Normal
Skill
Properties
*Resource(s)
Projects and Tasks
Properties

## Slide 57: LYNX Resource/Skill and Team Model Multi-Skill and Properties
Skill (Group)
“Properties”
Resources
Engineering
Design
Programming
....
Programming Language
Technology
Expertise (seniority)
......
Name 1
Name 2
Name 3
…
LYNX “protects” resources with unique competencies or domain know-how!
Resources and skills are separated and have an “N to N” relationship:
  A resource can have multiple skills
  A skill can be implemented by multiple resources
Special “Properties” identification via (unlimited) properties at skill and resource level
Team assignment: Resources are assigned to a team
This model is following the ISA 95 Standard
Team

## Slide 58: Examples

## Slide 59: The Principle of (dynamic) „Late Binding“ and Capacity Flexibility Timing Skill Specification and Resource Confirmations
Project Planning Phase
Project Release Phase
Execution Phase
Skill Specifications
Resource Confirmations (names)
Confirmations preferably as late as possible
(when Tasks are Ready to Start !)

## Slide 60: Create your First Project
Project Properties

## Slide 61: Add your first Project
Project portfolio:
  Choose “Add”
Project Properties:
  General: add general information
  Project dates: enter initial dates as expected or known
  Scheduling: review scheduling settings

## Slide 62: Create your first project
ID
Description
Optional:
  Start date
  End date

## Slide 63: Add your first project
Select Project Portfolio in the Desktop Window (F5)
Select Add
Ensure the “Critical Chain Engine” is selected.
Select your preferences. In CCPM Just in Time is considered as “Best Practice.”
1
2
3
Add a Project ID and Project name (description)
Add an initial desired or requested end-date (due date)

## Slide 64: Why “Just in time” is a good idea..
Widely spread and adopted in logistics and production:
  Less inventory
  More flow
  Less Work-in-Progress (WIP)
  Reliability
  …..
JIT for Projects requires:
  CCPM Thinking and JIT Scheduling Options:
    Critical Chain
    Feeding Chain

## Slide 65: Scheduling Settings Options
2 X JIT
2 X ASAP
ASAP + JIT
Today

## Slide 66: Your first project is listed in the Project Portfolio / Not started
TIP: Try right mouse-click on column headers for additional sorting and filtering
Filter applied to list of projects
Default filters to apply to list of projects:
Status “ Not Started”
Status “Released”
Show all
Show Templates
Your FIRST project (D1) has been created and is listed in the Project Portfolio, with status “ Not started”
Double clicking opens the project
If you want to go back to or recover the default sorting and filtering

## Slide 67: Level 1: Project Workflows or Mastertiming Network Logic building a Critical Chain or Shortest Path
START
Concept
Integration
Hardware
Buffer
Software

## Slide 68: Create the Project Plan
Add Task(s):
  Optional:
    Summary Tasks
    Level of Effort (LOE) Tasks
    Auto-expand
    Fixed Duration
Create the Project Network:
  Add task dependencies (predecessors / successors)
Add Skills (and *Resources)
Convert the plan into a Critical Chain Plan:
  Apply “Shorten Task Duration”?
  Select and insert Buffers:
    Project Buffer
    Feeding Buffer(s)
    Milestone Buffer(s)

## Slide 69: Multi-Level Planning Level 1: Task and Workpackages Level 2: Cards
START
Normal
Normal
Normal
Buffer
Workpackage
Bundle of Cards
Worpackage with a bundle of cards
Level 1
Level 2

## Slide 70: Add Workpackage(s)
Add Workpackage(s):
  Select Tasktype: Workpackage
  Set “Unit of Measure”
  Set initial “Size” per Workpackage
Add Cards:
  Userstories
  Subtasks
  Etc.
Add Skills (and *Resources):
  Standard Skill (Normal or Virtual)
  Optional:
    Team Skill

## Slide 71: The “Project Window” – Multiple Views and Windows
Task Grid
Gantt Chart
Task Properties
D01 Product Development Project Window
Confirms Task Property updates
Undo and Redo buttons
Multiple tabs
Also click in the Gantt area to confirm changes
Auto scale timebar

## Slide 72: Add Tasks

## Slide 73: Target Plan
Feeding Chains
Just in Time

## Slide 74: Create a plan
There are many ways to Rome, I tell you the most convenient for now:
Options:
  Use the target plan example
  Use your own project plan
Add at the minimum 5 tasks

## Slide 75: Add Tasks
Start here to create your first task.
Any new task gets a default duration of 1 day after giving the task a name. You can change the expected duration in the duration column.
Click in the Gantt Chart, to confirm your update! *
* Background of this process is the optimization of the performance and prevents that any (small) change triggers a re-calculation of the complete (large) project plan
Green Line = TODAY

## Slide 76: Add more tasks
Use the “down arrow” key on you key-board to quickly add new rows
Add a new task by pressing the +. Via the dropdown you can also add a task before (Ctrl Insert).
Press “Enter” or Click to confirm your changes
Delete a task with X
Tasks 2 – 6 are considered feeding chain tasks, not (yet) part of the “ Critical Chain”.
In this example “Feeding Chains” are positioned “ Just in Time,” offset against the Critical Chain (task 1).

## Slide 77: Save
Each tasks gets its own ID
Change Task duration here
Right click on header of the task list, to remove any unwanted filter or sorting.
Click on Auto scale for an adjusted timebar

## Slide 78: Create a plan
There are many ways to Rome, I tell you the most convenient for now:
Options:
  Use the target plan example
  Use your own project plan
Add at the minimum 5 tasks
Add also:
  Dependencies
  Skills (*Resources)

## Slide 79: Add Dependencies
(and remove)

## Slide 80: Add Dependencies between tasks
Between task 1 and 2 there is a Finish-Start relation.
See also the CTRL Fast-Keys!
Button for adding dependencies between tasks. The default is a Finish-Start dependency (just click on button, without opening drop-down)
Task 1 and 2 are selected for adding a dependency (use SHIFT or CTRL to select two or more tasks)
Use the drop-down to see all options.
In CCPM typically only Finish Start is used.

## Slide 81: You can also select Tasks with your mouse in the Gantt Chart to add a dependency
Dependency will go from the task selected first to the next selected task(s)

## Slide 82: Add dependencies via the Edit Boxes Predecessor box and Successor box
The edit boxes are very useful especially in case of projects with many tasks.
Use this filter

## Slide 83: Deleting dependencies Via Task properties  Tab “Dependencies”
Delete Successor relationship between task # 3 and task #6.

## Slide 84: Add/update dependencies Select view  Data entry view

## Slide 85: Review result and statistics
Use the Auto scale timebar (F4), to scale your plan to fit in the Gantt window.
Task properties/Dependencies for task #6
Project statistics are displayed here.
Current length of the Critical Chain is 28 days

## Slide 86: Select “Critical Chain View”
Only tasks on the Critical Chain are displayed

## Slide 87: Add Skills & Resources

## Slide 88: Add skills (and resources)
A System Engineer will be added to the selected task(s)
Drag & Drop Skills to the selected tasks (1 or more)
Select the Skill/Resource/Task Manager Window
1.
2.

## Slide 89: Adding Skills via the Resource requirements column

## Slide 90: Review the resource load for your project
Resource Requirements for Task 2 are red shaded in the load graph

## Slide 91: Modify Task Estimated Time and Units % (optional)
You can modify the estimated time and unit percentage

## Slide 92: Review the resource load for your project (scenario Virtual Skills) Skills are “Virtual skills”
In case of “Virtual Skills” LYNX does not make a pre-selection and soft-allocates a resource name. Please refer to SLIDE 19

## Slide 93: Add Task Managers
Prepare for Execution (Doing the work)

## Slide 94: Invite multiple Task Managers involved to the TM List In a CCPM implementation typically a Task Manager is responsible for (daily) task updates
Invite a TM for task #1, only!
Add a TM to the TM List for the project
You can invite an existing user or invite a new user as a TM

## Slide 95: Add a Task Manager to task(s) Via the Task Manager column or via “Drag & Drop”
Add yourself as Task Manager to the first task
Mike Dempsey (current user) is added to task #1

## Slide 96: Apply CCPM Behavior
Add buffers

## Slide 97: Apply Critical Chain Behavior in 3 Steps
3
Decide about Task Time Reduction
You can keep or change the default percentages and confirm
Length of the Critical Chain has been shortened with 50 %
1
2

## Slide 98: Start a project from a template

## Slide 99: Start a project from a template Where to find available templates?

## Slide 100: Start a project from a template
1
2
3
Select Copy Project after filling in the Project ID & description

## Slide 101: Start a new project from a template
You can find your new project under “Not Started”

## Slide 102: Special Items
Summary Tasks
Milestone Buffers

## Slide 103: Special Items
Summary Tasks
Projects with multiple end-points:
  Milestone Buffer(s)
  Project Buffer

## Slide 104: Release your project
Create active tasks

## Slide 105: Release your project and its tasks
After Release LYNX has created two buffer controls (project buffer column and feeding buffer column)
The release of the project has resulted in an update and extension of the statistics
Select Project Properties
1
2
3

## Slide 106: Select My activities in the Desktop Window Update Ettc for your first task
1
2
3
The Task Manager can:
Assign and confirm resources for a task
Start a task by changing the status
Enter the Estimated Time to Complete (e.g. on a daily basis)
Opens the project plan

## Slide 107: A few tips and tricks

## Slide 108: Search and Replace (CTRL F)

## Slide 109: Mark Favorites

## Slide 110: A few tips and tricks
Copy a selection of tasks with CTRL C (Copy) and CTRL V (Paste)
Click in the Gantt Chart and then Use CTRL + Scroll to Zoom
Go to a “date line” and zoom in/out by moving the date line
FIND MORE TIPS AND TRICKS: https://support.a-dato.com/hc/en-us
Use right mouse click to filter / hide columns

## Slide 111: Continued
Right Click on a project row
All windows can be individually moved. You can use 2 screens side by side.
Right click on header of the project list, to remove any unwanted filter or sorting.

## Slide 112: Resolve Warning Messages Plan cannot be calculated due to planning logic violations
The messages can be viewed in the “Messages” tab
LYNX may not be able to recalculate the project due to a message.
In this example there is only 1 designer available. The planner has assigned 2 !

## Slide 113: Start adding “Notes”
1
Click on this icon to add a note
2
3
Select the type of note you want to create
Click the + icon to create a note

## Slide 114: Special Items
Buffer Recovery
Level of Effort Tasks
One Click “Click-through” from a task in the task-list, directly into the project
Down-stream / Upstream chain views based on any selected task in the schedule
Ability to share de-buffered plans with external parties or customers
Possibility to exclude tasks from task time reduction
Cross-skill Resource Management
Split Critical Chain tasks in case of multiple resource with different workload
Auto Complete Option
  intended for tasks with long and or fixed lead times only (such as shipping or purchasing tasks)
Display of “Last Progress Update”
  for tasks that are started, which provides fast feedback when the last ETTC update has taken place