## Slide 1: Get started with LYNX
LYNX Task Management Training

## Slide 2: LYNX is used for multi-project management.. Objectives and Challenges
Teams
&
Resources
Multi-Project and Portfolio
Project
Optimal Conditions for innovation
Deliver quality
Be able to focus and getting work done
Must be Reliable and Fast
Manage Scope, Time and Budget
Needs to know if the project is on “track”
Satisfy the stakeholders
Portfolio with many projects
High Due-Date performance
Deliver more projects
1. In Time 2. Within budget 3. Deliver Scope 4. Right Quality 5. Across Projects

## Slide 3: Making Collaboration and Decision Making Easier Working together at the same time in the same project(s)
Real Time Data
Projects, tasks, sub-tasks, cards
Resource manager
Team manager
Task manager
Skill/ Resource
Project manager
Portfolio manager
Team member
Transparency
“Timing is everything”
There is only 1 moment you can be on time!
If you are not there you are either too early or too late.
Johan Cruijff
External partner

## Slide 4: Scope
Plan the Work
Work the Plan
Communicate
Introduction
Project
Tasks
Workpackages
Cards
Task Management
Cards Management
Kanban Board
What is
LYNX about?
Progress
Reports
Export
Project manager
Task manager
Skill/ Resource
Team member

## Slide 5: LYNX Role Based Training
LYNX for Project Managers
LYNX for Portfolio Managers (multi-project)
  Master Schedulers
  Release Managers
LYNX for Resource Managers
LYNX Task Management
  LYNX Task Managers
  LYNX Resource Users
  LYNX Team Managers
  LYNX Resource Managers
LYNX TameFlow
  For teams
  For you
My activities Roles

## Slide 6: Task Management Training - Topics
LYNX Overview
Philosophy behind LYNX
Login Stuff
A project example
Task Management:
  My Activity View
    Before starting a task
    Starting a task
    Progress reporting (Ettc)
  Communication (Notes)
  Add (delegate) Task Managers
  Impersonation(“Vertreterregelung”)
Resource management tools
  Resource Load Diagram
  My Resources
  Debuffered View
  Reporting

## Slide 7: Imagine you are Robin Porter… My activities

## Slide 8: LYNX Project and Portfolio Management Critical Chain Project Management
Integration of Agile and Kanban Workflows – Agile CCPM
All rights reserved - Confidential
Notes: Als we het hebben over projecten dan zien wij dat bedrijven en projectorganisaties zich op zich voorbereiden voor de realisatie van een project. Scope wordt beschreven, rollen en verantwoordelijkheden, risico analyse, governance structuur, etc. Dus je kan zeggen dat organisaties goed voorbereid voor de praktijk / avontuur ingaan. Zo volwassen is men geworden.
Het punt is het blijft een avontuur. Dus alle risico’s die van te voren benoemd waren komen voor. En ook Murphy komt om de hoek kijken. En daar sta je dan. Onze boodschap is: als je dan het avontuur ingaat zorg dat je de juiste instrumenten bij je hebt. Een kompas en GPS, zodat je tijdens je avontuur de juiste beslissing kan nemen en controle over je bestemming kan houden.

## Slide 9: Making Collaboration and Decision Making Easier Working together at the same time in the same project(s)
Real Time Data
Projects, tasks, sub-tasks, cards
Resource manager
Team manager
Task manager
Skill/ Resource
Project manager
Portfolio manager
Team member
Transparency
“Timing is everything”
There is only 1 moment you can be on time!
If you are not there you are either too early or too late.
Johan Cruijff
External partner

## Slide 10: LYNX brings everything together…
Projects with stages, phases, tasks, workpackages
with cards
Portfolio / Multi Project
Scenario Planning & Simulation
Taskboards with Cards e.g. subtasks, user-stories
Card
Multi-Skill Resource Management
Skills, profiles, resources, teams, team members
Portfolio manager
Project manager
Resource manager
Team manager
Task manager
Team member
Resource

## Slide 11: And also integrates the Agile/Kanban way of working into projects… Multi-Level Planning
The TameFlow Approach
Through LYNX TameFlow, Agile and Kanban workflows are integrated, bringing Agile CCPM to life.
Project manager
Team member
Level 1
Level 2
Level 2
Task manager
Resource User

## Slide 12: LYNX TameFlow Task Board with Flow Buffer Management

## Slide 13: LYNX offers a different approach.. The 5 Foundation Pillars of LYNX
Dynamic Critical Chain Scheduling
Buffer Management
Manage Queues with Priorities
Late Binding
Manage Flow and Work-in-Progress
(WIP)

## Slide 14: Including heatmaps and simulation.. Managing Work-in-Progress
LYNX Scenario Wizard
LYNX Release Wizard
LYNX Debuffered Mode
Portfolio manager
Notes: In this example the staggering is done at Skill level. It concerns a portfolio with 11 active projects. All project are equally important to the company, and have been assigned a so-called business priority of 10 (we will use the business priorities later in this presentation)
In the background the resource load diagram shows that an overallocation exist on the skill System Engineer.
In diesem Beispiel erfolgt die Staffelung auf Skill-Ebene. Es handelt sich um ein Portfolio mit 11 aktiven Projekten.
Alle Projekte sind für das Unternehmen gleich wichtig und haben eine sogenannte Geschäftspriorität von 10 erhalten (wir werden die Geschäftsprioritäten später in dieser Präsentation verwenden).
Im Hintergrund zeigt das Ressourcendiagramm, dass es auf dem Skill System Engineer ein Überlast gibt.

## Slide 15: Giving you the potential to improve…..
Overload
Multi-tasking
Task Interruptions
Cherry picking
Early starts
De-synchronisation
Batching
Parkinson’s law
Student syndrome
Local safeties
Kopfmonopole
Global priorities
WIP Control
Roadrunner
  Single tasking
Single-touching
  Global buffers
Late binding
Full-kit
Single-piece flow
  Late binding
Tomorrow
A different approach
Today
More Flow, better timing
Less pressure and stress
Easier collaboration
More reliable projects
More transparency
Win (back) capacity
Finish projects faster
…..
Improvement Potential...
Symptoms
New Reality

## Slide 16: Summary Customer Overview
Fields of application
  Design and Engineering
  Building and Construction
  Service and Maintenance
  Organisation
Global footprint
  Currently over 100 customers, across all continents
  From small to very large implementations (with over 400 users and hundreds of projects)
16

## Slide 17: Philosophy (behind Lynx)
Projects consist of people!
Thus, when managing projects, it is about people
(and processes).

## Slide 18: Task Durations (within Projects)
100 %
Wait
Work
Work
Typical
“Flow Ratio”
Work
Work
Work
Work
Wait
Typical task Execution Pattern
Work
Task
10 - 20 %
Notes: Vaak niet boeven 20 % - EERDER ROND DE 5
Zin is krom.  om echtt te verbeteren kan je veel nbeter richten op verminderen van de wachttijden

## Slide 19: Where to start improving? “Low” hanging fruit
Wait
Work
Most jobs are not slow, but typically just have to wait a lot.
Notes: Overlay met euro tekens, waar zet je geld op in?  groen kost heel veel.

## Slide 20: Today: What makes people (and organisations) unhappy?
Undesired
Too many things going on = mental pressure
Delays and waiting time
Many unfinished tasks, more Work-in-Progress
Task Interruptions
Favorite tasks first
Working on non-critical work first
Efficient but not effective
Every person adds private buffer – long leadtimes
Low Flow Ratio
Budget time  Actual time
Last minute rushing, forget stuff
A guaranteed “bottleneck”
Impact
Overload
Multi-tasking
Task Interruptions
Too early starts
Cherry picking
De-synchronisation
Batching
Local safeties / Padding
Spreading resources thin
Parkinson’s law
Student syndrome
“Kopfmonopole”

## Slide 21: Tomorrow: What makes people (and organisations) happy?
Desired
“Constraint” thinking  Work on less than X things at the time
Inverse of multi-tasking
Less interruptions = higher flow %
Everything is prepared to finish in one go (mise en place)
Prevents loud-mouth-management
The show CAN go on
Effective instead of efficient
Team focus on project “constraint”
Good enough estimates will do
No handover delays
Impact workfloor directly visible on strategic level
Flexibility and high flow ratio
Impact
WIP Control
Single tasking
Single-touching
Full-kit
Objective priorities
Synchronisation
Single-piece flow
Global buffers
Aggregation
Relay race
  Vertical Integration
  Late binding

## Slide 22: How to get there?
Desired
Different way of planning
Undesired
Different way of working
Overload
Multi-tasking
Task Interruptions
Too early starts
Cherry picking
De-synchronisation
Batching
Local safeties
Padding
Parkinson’s law
Student syndrome
Kopfmonopole
WIP Control
Single tasking
Single-touching
Full-kit
Objective priorities
Synchronisation
Single-piece flow
Global buffers
Aggregation
Roadrunner
  Vertical Integration
  Late binding

## Slide 23: A different approach… Critical Chain (Multi-)Project Management: Key Ingredients
Buffer
50%
Execute by Single Priority
Traffic light = 1 Operational Priority for everybody (across projects)
Buffer Management
+ Critical Chain
Manage across projects
(Control the WIP)
Heatmap or Feverchart

## Slide 24: CCPM: Theory of Constraints What do we mean with a “Critical Chain”?
The “critical path” (longest path) is the “bottleneck” in a project because it determines the total duration of the project………
Or isn’t it……?
The capacity of the “bottleneck” determines the maximum output that can be achieved
A
A
B
C
D
8
5
2
1
5
15

## Slide 25: CCPM: Critical Resources
Question:
Who are the critical resources or critical departments within your company?
What is impact of their availability on your project or other projects?

## Slide 26: CCPM: Critical Resources  impact on your project.. Ability to identify “Invisible dependencies”
A
A
B
C
D
8
5
2
1
5
Critical Path = 14
19
A
A
B
C
D
8
5
2
1
5
15
Critical Chain = 19
Task B is not Critical !

## Slide 27: How to improve? The 5 Foundation Pillars of LYNX
Dynamic Critical Chain Scheduling
Buffer Management
Manage Queues with Priorities
Late Binding
Manage Flow and Work-in-Progress
(WIP)

## Slide 28: Introduction of Buffer Management
What can you do with Red, Orange and Green?
Any task needs some contingency or safety embedded to cope with:
Complexity
Uncertainty and variation
Murphy
However…

## Slide 29: A Standard Plan
CRITICAL CHAIN / PATH = 60
10
20
30
40
50
60
Time
Achievable
Contingency
Psychological effects of the standard plan:
Safe estimates (or overambitions)
Student Syndrome
Parkinson's law
Padding
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 30: A Buffered Plan (1)
45
10
20
30
40
50
60
Time
Achievable
Contingency
2/3
1/3
Pooling of Contingency Insurance Model
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 31: A Buffered Plan (2)
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 32: A Buffered Plan (2)
60
10
20
30
40
50
60
Time
Achievable
Contingency
2/3
1/3
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 33: Green 50 % progress on the longest chain / 15 % buffer used
Done
45
10
20
30
40
50
60
Time
50 % / 15 %
Project is on track. The risk that the project will be late is very low.
“To be safer, (re)move the safety”
Done
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 34: Red 55 % progress on the longest chain / 65 % buffer used
Done
45
10
20
30
40
50
60
Time
55 % / 65 %
Relatively to much buffer is used. Measure are need to make sure the project can be delivered on time.
“To be safer, (re)move the safety”
Done
Done
Done
Today
Notes: Laat zien hoe buffer naar achteren wordt geplaatst en ingekort. Om dit te bewaken heb je een goede projectmanagement tool nodig, want: hoe weet je of en hoeveel je al van die centrale projectbuffert hebt gebruikt?

## Slide 35: What can you do with Red, Orange and Green? CCPM: Project Trend Line
Fever Chart

## Slide 36: What can you do with Red, Orange and Green? Resolve day-to-day resource conflicts (and prevents (bad) multi-tasking)
D2
D1
T1
How to solve the “resource conflict” for Mike?
D2
D1
Today
T1
D2
D1
T1
Today
T1
D2
D1
Execution sequence of the queue for Mike
The perfect original plan for ONE System Engineer called “Mike”
Manage the Queue !
The actual situation Today
„In the Autopilot-Modus, Resource Managers , Task- and Project managers are supported by Operational Priorities for the synchronized execution of their projects”

## Slide 37: “To do” List: My activities Sequence from red to green
Notes:     1. Doorlooptijd van elke taak – er gaat meer dan 30 % verloren aan verstoringen, andere zaken
    2. Weniger Projekte geleichzeitig
    3. Stoppen met Teiltermine, focus op endtermine en een prioriteit
    4. Focus op fertig machen

## Slide 38: What can you do with Red, Orange and Green? Manage all projects together

## Slide 39: What is needed? Fast-Feedback Loop (ETTC)
Flawless handovers:
Ensure Delivery is complete
Be Ready-to-Start
  Good preparation
Continuous (frequent) update of the “Expected Time to Complete” for each active task (ETTC)
Task
Management
Notes: SHOW
We know now what we should not do but what do we need to do?

## Slide 40: How to achieve improvements?
Aggregation and (dynamic) “Late Binding”
  “If we bind tasks to resources at long time horizons (early) we are affected by the cumulative variance of all preceding tasks. By committing at a short time-horizon (late), we can avoid this accumulation of variance”.

## Slide 41: Achieving more “Flow” and Resource Management Allocate work to team (or skill) first (not individuals)
Aggregation of resource requirements on „Skill(group)“ or „Team“ Level
  Resources are “pooled” by „Skill“ or Team
  Specification of any “Task Resource Requirement” by “Skill”
Principle of (dynamic) “Late Binding”
  Keep your options open as long as possible Non-Binding *Soft-Assignments”
  Prevent “Kopfmonopole”
  “If we bind tasks to resources at long time horizons (early) we are affected by the cumulative variance of all preceding tasks. By committing at a short time-horizon (late), we can avoid this accumulation of variance”.

## Slide 42: The “Late Binding“ solution within LYNX Specification of “Resource Requirements“
Resource Names
Implementation of the ISA95 Skill / Resource and Aggregation Model
  Skills
  Resources
  Profile Properties
Task Resource Requirements
Virtual Skill
# FTE
Projects and Tasks
Task Resource Requirements
Normal
Skill
Properties
*Resource(s)
Projects and Tasks
Properties

## Slide 43: LYNX Resource/Skill and Team Model Multi-Skill and Properties
Skill (Group)
“Properties”
Resources
Engineering
Design
Programming
....
Programming Language
Technology
Expertise (seniority)
......
Name 1
Name 2
Name 3
…
LYNX “protects” resources with unique competencies or domain know-how!
Resources and skills are separated and have an “N to N” relationship:
  A resource can have multiple skills
  A skill can be implemented by multiple resources
Special “Properties” identification via (unlimited) properties at skill and resource level
Team assignment: Resources are assigned to a team
This model is following the ISA 95 Standard
Team

## Slide 44: Examples

## Slide 45: The Principle of (dynamic) „Late Binding“ and Capacity Flexibility Timing Skill Specification and Resource Assignments
Project Planning Phase
Project Release Phase
Execution Phase
Skill Specifications
Resource Assignments (names)
Hard assignments preferably as late as possible
(when Tasks are Ready to Start !)
“Non-Binding *Soft-Assignments”
“Hard assignments”

## Slide 46: Before we start…
Login and Workspaces

## Slide 47: Visit the LYNX Help Center
Visit the
LYNX HELP CENTER
https://support.a-dato.com/hc/en-us

## Slide 48: Login with your (new) credentials you received per email
If you already received an invitation to join LYNX from another user (e.g. colleague, admin, workspace owner) your login credentials are provided in the invitation email.
If you are invited as a first-time user, LYNX will provide an initial password, which can be changed in MyProfile

## Slide 49: New User Registration
Do not forget to enter your initials.

## Slide 50: Login after registration with your email and your password

## Slide 51: Select “My profile”
This screen this screen may still be empty (as long as no tasks are assigned to you)
The name of you “Space” is displayed here.

## Slide 52: Check (change) your “Space”
The name of you “Space” is displayed here.

## Slide 53: Get started with Task Management
Assign and confirm a resource name
Start a task by changing the status
Update progress (Ettc = Estimated time to complete)

## Slide 54: What is needed? Task Management
Flawless handovers:
Ensure Delivery is complete
Be Ready-to-Start
  Good preparation
Continuous (frequent) update of the “Expected Time to Complete” for each active task (ETTC)
Task
Management
Assign and confirm a resource name
Start a task by changing the status
Update progress (Ettc = Estimated time to complete)
Notes: SHOW
We know now what we should not do but what do we need to do?

## Slide 55: LYNX Task Management via the “Task Manager Role”
START
Concept
Integration
Hardware
Buffer
Software
Task manager

## Slide 56: Intermezzo Your tasks in a project plan created by a project manager

## Slide 57: “To do” List Sequence from red to green
Notes:     1. Doorlooptijd van elke taak – er gaat meer dan 30 % verloren aan verstoringen, andere zaken
    2. Weniger Projekte geleichzeitig
    3. Stoppen met Teiltermine, focus op endtermine en een prioriteit
    4. Focus op fertig machen

## Slide 58: Manage the Task From…..
Opens the project plan
Refresh
Save!

## Slide 59: Manage the Task To…..
Steps:
Assign and confirm a resource name
Start a task by changing the status
Update progress (Ettc=Estimated time to complete)
Ettc is default in Days
You may also enter hours: 40h

## Slide 60: Upcoming tasks Not ready to start yet..(RTS = No)

## Slide 61: Have a look into the plan

## Slide 62: Have a look in the plan

## Slide 63: Your Task Manager Assignments Access to your tasks

## Slide 64: Review Resource Requirements
As TM you can update these values

## Slide 65: How to change assignments?
Select another designer..

## Slide 66: Change via Resourcing Dialog
See video with other re-assignment options

## Slide 67: Add other Task Managers
Delegate Task Management

## Slide 68: Open the plan and the Task manager box

## Slide 69: Change to “Leading” Task Manager Move Mike up in the list

## Slide 70: Result

## Slide 71: Other TM Assignment options Note: requires additional rights for the TM: Read and Write access

## Slide 72: Impersonation Mode Robin Porter is taking over tasks of Mike Dempsey (Temporarily)

## Slide 73: Task Management via Other Roles
The “My activities Roles”

## Slide 74: LYNX Task Management for “My activities Users” the “My activities” roles
START
Concept
Integration
Hardware
Buffer
Software
Task manager
Team manager
Resource User
Resource manager
The
My Activities Roles

## Slide 75: My activities for “Resource users”
Resource User
Mike can only update his own assignment for the task, in the role of Resource User.
Mike has no access to the System Engineer box.

## Slide 76: My activities for other roles
Resource manager

## Slide 77: My activities for other roles
Team manager

## Slide 78: Task Management for Workpackages
With Standard Skills

## Slide 79: Task Management of Workpackages
START
Normal
Normal
Normal
Buffer
Workpackage
Bundle of Cards
Worpackage with a bundle of cards
Level 1
Level 2

## Slide 80: What is different? Workpackages versus Normal Tasks
What is not different?*
  My activities procedure:
    Assign resources
    Starting a workpackage
    Progress reporting
What is different?:
  Cards Management
  Input for Ettc determination:
    Size monitoring
    Counters in the workpackages
  Additional views:
    LYNX Cards Views
    LYNX TameFlow Taskboards
*if selected skills are of type “Standard Skills” (Normal or Virtual)
Rules for publishing cards on LYNX Taskboards:
  Project must be “Released”
  Workpackage must be started
LYNX Cardsview
  Working with Cards
  Sequencing Cards

## Slide 81: Cards Management LYNX Cards View and LYNX TameFlow
The TameFlow Approach
Through LYNX TameFlow, Agile and Kanban workflows are integrated, bringing Agile CCPM to life.
Project manager
Level 1
Level 2
Level 2
Task manager
My activities Roles

## Slide 82: LYNX Cards View and Editor My activities
A task manager can add, change and remove cards via this view.

## Slide 83: Cards Configuration

## Slide 84: Working with the Cardsview

## Slide 85: Size Monitoring

## Slide 86: Burn-up Graphs

## Slide 87: Let’s go… Rick and Tom are assigned, workpackage is started by Mike
The Software Workpackage Team:
Rick + Tom + Mike (TM)

## Slide 88: Workpackage appears in the Taskview and Cardsview of Tom and Rick (and in LYNX TameFlow)

## Slide 89: The Software Workpackage Team can get going..

## Slide 90: Let’s start another workpackage.. In a few days, and preferably Just-in-Time to keep WIP down

## Slide 91: LYNX TameFlow – Toms Workpackages

## Slide 92: Size monitoring Team can add more cards….

## Slide 93: Determine Ettc from Card Counters

## Slide 94: Additional Topics
LYNX Notes and Documents for Task Managers

## Slide 95: LYNX Notes System

## Slide 96: LYNX Document System

## Slide 97: Resource Management Tools

## Slide 98: Resoure Load Diagram (s)

## Slide 99: The All Graph
Shows Resource Load across your resources